# Appendices

Appendices	1

Appendix A:  JISC OBC Approval	3

Appendix B:  Letters of Support from Healthcare System	12

Appendix C:  NHSI Capital Business Case Core Checklist	16

Appendix D:  Excerpt from Public Trust Board Minutes 4th August 2020	17

Appendix E:  Addendum to the OBC following Discussions with Regional NHSE&I Teams	19

Appendix F:  Planning	27

Appendix G:  National and Local Strategies	39

Appendix H:  ULHT Estates Strategy	49

Appendix I:  Cabinet Office Risk Potential Assessment	100

Appendix J:  Evaluation of Possible Site Options	115

Appendix K:  Clinical Model Options	130

Appendix L:  pathology Solution for Pilgrim Hospital Urgent Care Project	134

Appendix M:  Medicine Division Staffing Plan	147

Appendix N:  SOP for Management of Patients in ED	153

Appendix O:  Benefits Plan and Register	166

Appendix P: Risk Register	166

Appendix Q:  Project Execution Plan	174

Appendix R:  Projects Leads CV’s	175

Appendix S:  Communications Plan	183

Appendix T:  Sustainable Development Management Plan (SDMP)	189

Appendix U:  Project Team Meetings Terms of Reference	204

Appendix V:  Premises Assurance Model	222

Appendix W – ULHT Draft Green Plan	223

Appendix X – Schedule of Accommodation and Derogations	224

Appendix Y – ITT & Contracts	226

Appendix Z – Equipment List	227

Appendix AA – CIA Model	250

Appendix AB – Schedule of Accommodation & Derogations	251

Appendix AC – FB Forms	252

Appendix AD – BREEAM Assessment Report	253

Appendix AE – MMC Utilisation Assessment Tool	254

Appendix AF – Post Project Evaluation Plan	255

Appendix AG – Social Value Plan	256

Glossary	257

# Appendix A:  JISC OBC Approval

# Appendix B:  Letters of Support from Healthcare System

Removed for GDPR

Lincolnshire CCG 
Bridge House 
The Point
 Lions Way
Sleaford
NG34 8GG

Telephone: 01522 573939  
Email: lccg.office@nhs.net

14 March 2022

Associate Director of Contracts & Income

United Lincolnshire Hospitals NHS Trust

Lincoln County Hospital

Greetwell Road

Lincoln

LN2 5QY

Dear XXXX,

Project to Develop Resuscitation Facilities, Improve Accommodation within the Urgent Treatment Centre and Reconfigure the Emergency Department at

Pilgrim Hospital, Boston

Following on from further work completed by ULHT with regards to the business case to develop and improve the Emergency Department at Pilgrim Hospital, NHS Lincolnshire CCG is writing to confirm its continued support for this project.

As per our letter of July 2021, we recognise the aim of this project is to develop resuscitation facilities, improve accommodation in the Urgent Treatment Centre and reconfigure the Emergency Department at Pilgrim Hospital, Boston.  This aligns to the national direction of travel for urgent care and addresses the issues and inherent difficulties faced at this hospital – an aging department and environment for our local population, insufficient capacity for patients to be seen in a timely and safe manner, and the impact on staff morale including recruitment and retention.  All of these factors have had an adverse effect on our top priority; excellent care for the patients of Lincolnshire.

This scheme, whilst led by United Lincolnshire Hospitals NHS Trust, has consequences for the wider health and social care system and reflects the system approach we are taking to develop and transform our services.  In addition, we have staff from Lincolnshire Community Health Service NHS Trust and Lincolnshire Partnership NHS Foundation Trust within this department so this project will also create a better working environment for our health-system colleagues. We are aware that you are taking an update to our System Urgent Care Board to update on this project along with having conversations with other system stakeholders including Healthwatch and EMAS.

We have collectively identified a wider range of benefits to the general public in the area too, supporting our ambulance service and impacts on other services outside of health such as the police force.  The scheme has an impact on the public who can see that the government is investing heavily in the area and fits with the “levelling up” agenda.

We are aware that the original allocation of funding, from the £850m for 20 health organisations announced by the Prime Minister on 5th August 2019, was for £21.3m.  This sum came from 2 separate strategic cases for UTC and expanded resus facilities developed some years earlier.  Through various workshops to develop this FBC a revised capital amount is requested inclusive of OBC/FBC fees.  This is a significant increase on the allocation and is a result of:

- Scope creep; the working group considers the whole of the ED at Pilgrim Hospital needs to be developed at the same time, rather than developing pockets in isolation.  This gives greater value for money and addresses the key issues facing the department;

- The time from the original strategic cases is significant and costs have increased;

- The original cases contained only a small amount for contingencies.  In consultation with HM Treasuries “Green Book” and the fact that this project is high risk an optimism bias of 24% was applied at OBC.  Subsequent uncertainties over decanting staff within one of the buildings has shown this value was wise to include.

We understand that work on the expansion will be completed within the 2024/25 financial year and will have some increased costs linked to staff although this will ensure improved patient flow and experience, reduced ambulance handover delays and a service that is future-proofed for the next 30 years. We will therefore work with you to ensure we understand the implications for the contract but also continue our work together to understand the benefits for the wider Lincolnshire system. Whilst we appreciate there are some unknowns of the 2024/25 Contracting and Payment mechanism, we will continue to work towards the open-book and transparent process on cost based contracting.

In summary, this project is approved by the system and will be integral in our continued journey to improve healthcare for the Lincolnshire population.

Yours sincerely,

Associate Director of Contracting and Performance

# Appendix C:  NHSI Capital Business Case Core Checklist

# Appendix D:  Excerpt from Public Trust Board Minutes 4th August 2020

The following is an excerpt from the minutes of the ULHT Public Trust Board Meeting where the Pilgrim A&E business case was discussed.  These meetings are available from the ULHT website.  The case had previously been approved by ULHT Trust Board in private session.

Item 10.2 Business Case Pilgrim A&E

The Director of Improvement and Integration presented the business case to the Board seeking approval to submit the outline business case to NHSE&I for capital of £36.3m on Pilgrim hospital site.

It was noted that there would be a revenue costs to the Trust but that this would bring about improvement to the Urgent Treatment Centre, expand resus, reconfigure the majors area in the ED and improve the diagnostic services on site.

The money allocated from the Prime Minister’s visit had seen the Trust awarded with £21.3m of funding to improve facilitates at Pilgrim. The case of need at Pilgrim was clear due to the poor infrastructure and the ED being too small for the level of demand.

The Trust recognised that there were ongoing issues regarding poor patient experience and this had been picked up through CQC reports and the outstanding section 31 notices. The Trust received positive feedback relating to the caring nature of staff but it was recognised that the experience of patients identified overcrowding as an issue.

Since the announcement of the funding work had been undertaken as part of a Lincolnshire Project Team, inclusive of patient representatives, to develop the outline business case. The Board were asked to note that £21.3m funding had been allocated but that the business case now requested £36.3m.

The original amount had been determined by the combining of two separate cases put forward by the Trust at a national level when the allocation was made. The increase had been due to the length of time since the original cases were developed where costs had increased. A high level of contingency had been included due to the length of the build and the uncertainty of the impact of Brexit and the pandemic affecting costs.

The Trust had followed the Treasury green book approach which provided a clear process that would provide the best value for money. This approach did not tie in to the arbitrary capital amount but looked at identifying the requirements for the organisation in order to deliver the best strategic and economical case and experience for patients. The regional and national teams had been kept up to date regarding the costs and were aware of the change throughout the process.

The business case described the need for the improvement, economic impact, how works might be contracted and completion of the works. The preferred option would be the demolition of an existing building due to the poor condition and high level of backlog maintenance.

This would result in a new majors and resus facility being built and the existing ED footprint being refurbished for a larger UTC. With the expansion of the resus bays it would be possible for a CT scanner to be located within the ED.  Space would also be available for joint working with other providers and a dedicated paediatric area and bereavement facilities.

The Trust would look to use national contractors and most likely source through a national framework agreement in order to achieve the build more quickly and against approved costing measures.  As the full business case was developed this would be explored further and presented back to the Board. The project intent and approach was supported by the Lincolnshire System and supported by both the regional and national teams. At this stage the additional requested capital had not been agreed and it was hoped that this would be secured through the next stage of the process.

If the regional team declined the request for additional capital an alternative way forward had been outline in the business case. This would ensure time was not lost however the scheme would be reduced to the order of £24.3m. Elements of the development including bereavement and joint working facilities would be lost and it was felt that this did not offer the best value for money.

The Trust Board were asked to support the business case for onward submission to the process through NHSE&I which would take approximately 6-8 weeks. This would initiate the contracting discussion in order to develop the proposal to a full business case which would be presented back to the Board in January 2021.

It was anticipated that the project would take between two and two and a half years meaning that the handover and opening of the building would take place in the winter of 2023.  The Chair noted the importance as a Board to try to improve the environment at Boston, particularly in relation to the ED. The Board needed to do everything it could to ensure the successful passage of the business case to NHSE&I and progress as soon as timescales would allow.

The Chief Executive strongly supported the business case however there was a need to ensure wherever possible that the timescales were truncated. Handover in November 2023 felt too far away given the much needed improvements required. Where it was possible for the Trust to influence timescales this would be done.

The Chair noted that members of the Board supported the business case for onward submission and supported the pace of the project. The Chair noted that this had been a great technical case that had received some revision to ensure it read strongly however felt that the opening pages lack impact. This would be addressed outside of the meeting.  The business case required approval and submission to the regulators in order to progress, it was the right thing to do to consider values for money and to apply for capital to support the professionally identified needs at Pilgrim.

The Board were aware of the paediatrics issue at Pilgrim and discussions had been held, this needed to be emphasised within the submission.

The Board were provided with significant assurance from the report and supported the preferred way forward at a cost of £36.3m with revenue costs of £0.4m.  The Board approved the onward submission of the outline business case to NHSE&I for review.

The Trust Board:

- Received the report;

- Supported the preferred way forward;

- Approved the submission of the business case to NHSE&I

# Appendix E:  Addendum to the OBC following Discussions with Regional NHSE&I Teams

Following a discussion with the regional NHSE&I team on 19th October the Trust was asked to review the options to look at how the design could be amended to bring costs down.  The trust looked at the existing option, an option the clinicians preferred to create more accommodation for offices (PWF+) and two do less options.  The full addendum paper is given here, however, the preferred way forwards within this OBC still made the most economic sense following a full financial evaluation.

Rationale

The Outline Business Case to expand the Emergency Department at Pilgrim Hospital, Boston was submitted to the regional NHSE/I team on 19th October 2020.

In August 2019 21.3M was allocated for the project based on two independent schemes to expand resus and to build a new UTC.  This STP bid had been developed some years earlier and was at best a PID / SOC pre-estimate.  It presented an absolute do minimum in terms of the need to transform urgent care at Pilgrim Hospital.

The OBC requested funding to develop the whole ED, coming to 36.3M. At a meeting on 17th December the regional NHSE/I finance team requested the trust look again at how this could be brought back to the 21.3M.

Developing the OBC

After the trust received news of the initial 21.3M funding an OBC was developed through workshops with the clinical teams, estates, finance and patient representatives.  Representatives from ULHT, LCHS, LPFT, CCG, patient groups and regional NHSE estates teams were involved.

The working group established a clear principle from the outset – there needed to be a complete redesign of the whole ED rather than independent extensions outwards for resus and UTC as only doing this would:

- leave Majors, Minors and other areas still in poor condition;

- land lock the remaining department and prevent expansion in an area that was too small and had been rated inadequate by the CQC;

- cost a large amount of capital on road infrastructure.

The OBC was developed in accordance with the underlying principles of HM Treasuries Green Book; to develop clear spending objectives, benefits and risks and use these to develop the best value for money option to satisfy the spending criteria.

An up to date cost advisor report assessed the original plan (expanding resus and building the UTC) as costing 33.2M, not 21.3M.  This was, as stated above, because:

- original plans were only at PID / SOC stage, had been developed independently and were not worked up in enough detail at the stage they were told to submit;

- inflation was not fully taken into account;

- a 21.725% optimism bias of £3,061,405 and inflation adjustments totalling £1,487,869 were excluded from the UTC PID for approval purposes;

- VAT for either scheme was not included in the WAVE 4 STTP bid (capital without VAT was 21.3M), excluding 4.2M.

Therefore, ignoring the weaknesses in developing the two cases independently, the submission of £21.3M in the Wave 4 STTP bid presented by CCG should have been a minimum of £30.05M.

The project team considered many options including variations on:

- The original plan – extension to two sides of the building;

- Building out larger buildings across the two roads to expand the whole ED;

- Refurbishing or demolishing an adjacent building.

The most cost effective option was to look at the adjacent building, CSS or “H-Block”.  This adjacent building contains only a small number of clinical services, a large amount of administrative space and is in need of significant repair - backlog maintenance costs are £993k inc.

Demolition of the building and new build ED in its place would remove backlog maintenance, provide a fit for purpose building for all elements of the ED and improve the frontage of the hospital. The existing ED would be refurbished for the UTC.  Small extensions to the front and rear of the building would increase clinical space without the need for substantial infrastructure costs.

The group defined the core, desirable and optional elements of the scheme.  In relation to the capital spend on the building and equipment only, these were:

|  | Core | Desirable | Optional |
| --- | --- | --- | --- |
| Potential Scope | Minimal functionality (based on demand) to operate a modern ED | Additional clinics, paediatric facilities and bereavement | Additional diagnostics (pathology) |
| Service Requirements | Expansion of Resus to 6 bays (min) | ED clinic room | EMAS facilities |
|  | UTC | Dignity suite / changing places | Ultrasound scan room |
|  | Redesigned Majors area | Frailty / AEC clinic rooms | Café / concessions |
|  | Paediatric clinical rooms | Pharmacy |  |
|  | Seminar room | Paediatric waiting area separate to main |  |
|  | Training room | Volunteers area |  |
|  | Plaster room | Bereavement suite |  |
|  | Administrative space | Emergency dentistry |  |
|  | Places of Safety (s136) |  |  |
|  | Staff room |  |  |
|  | Good access / egress to wards |  |  |
|  | CT scanner & X-ray |  |  |

Analysis of the current demand plus an increase for anticipated future demand / population growth showed that the following clinical space would be required, as an absolute minimum.  Any additional rooms would future proof the service.

|  | Current cubicles | Increase required | Total required |
| --- | --- | --- | --- |
| Resus | 4 | 4 | 8 |
| Majors | 8 | 8 | 16 |
| Minors & UTC & GP | 3 | 10 | 13 |

The plan developed included many of the core and desirable options.  Architects, engineers and cost advisors drew up the required plans.  The cost of the scheme came in at 36.3M and was submitted to the regional NHSE/I team on 19th October 2020.  Following discussions with the regional team on 17th December 2020 the Trust was asked to look at options to bring the cost closer to the original 21.3M whilst maximising the benefits and value for money.

Options

The original capital cost of 21.3M came back from cost advisors at 33.2M, for the reasons outlined above.  The preferred way forwards from the project group came to a cost of £36.3M, as submitted in the OBC.  The clinical teams, in the build up to developing the FBC, had then requested more space on the 1st floor and a design to take plant into the roof space was developed as a preferred way forwards “do maximum” option (option 4).  Following the meeting with the regional finance team the original option with plant on the first floor (option 4a) was again assessed with costs now standing at 36.8M

Other options had previously been discussed by the project working group which could bring costs down closer to the original 21.3M.  These options, from the original long list (options 5 and 8), were worked up in greater detail with more accurate cost advice.  Costs for the four options were:

| Option | Forecast Outturn |
| --- | --- |
| 4 – preferred way forwards “do maximum” | £48, 822, 997 |
| 4a – preferred way forwards in original OBC | £36,767,551 |
| 5 – do less option | £33,897,58 |
| 8 – do minimum | £27,931,892 |

Note: each of these options contain generous planning contingencies (10%), optimism bias (24%) and equipment costs which, it was felt, would reduce as the designs progressed into FBC.

Design option summaries

Option 4

Scheme characteristics:

- Demolition of the existing Support Services Block (H Block);

- New build A&E infilling the space between existing A&E and OPD previously occupied by the H Block;

- New build A&E clinical accommodation provided at ground floor level;

- FAU, bereavement, administration, staff and training facilities at first floor level;

- Air Handling Units and general plant at second floor level;

- Bed lifts and stairs provided to front and rear of main floor area;

- Existing A&E reconfigured to provide clinical accommodation of UTC over a single floor (ground);

- Front (east) of existing A&E extended to accommodate new entrance and reception complete with Paeds area and ancillary toilets etc;

- Rear (west) of existing A&E extended to accommodate psychiatric rooms.

Scheme benefits:

- Provides ED and UTC accommodation side by side with good connectivity.  Clinical team have advised that layout of resus, RAIT, Majors and Minors allows for good temporary compartmentation of areas from an operational perspective which would allow flexibility in use in the event of an infectious disease situation;

- Single point of entry with ED and UTC Triage and internal navigation hub for streaming;

- Large ambulance entrance lobby containing weighbridge and 5 trolley spaces, together with CBRN store;

- Bereavement suite provided, adjacent and above resus;

- Diagnostics suite available to both ED and UTC, located between the two for ease of access and containing both CT and X-Ray;

- Two room psychiatric suite achieved with separate entrance;

- Full training and seminar accommodation provided, this at first floor level away from clinical areas;

- Full range of staff changing, toilet and mess facilities at first floor level.  Additional local provision for staff toilets etc provided in both Resus / ED and UTC areas.

Option 4a

Scheme characteristics:

- Demolition of the existing Support Services Block;

- New build A&E infilling the space between existing A&E and OPD previously occupied by the Support Services Block;

- New build A&E clinical accommodation provided at ground floor level;

- FAU, bereavement, administration, staff and training facilities at first floor level;

- AHU and general plant also at first floor level;

- Bed lifts and stairs provided to front and rear of main floor area;

- Existing A&E reconfigured to provide clinical accommodation of UTC over a single floor (ground);

- Front (east) of existing A&E extended to accommodate new entrance and reception complete with Paeds area and ancillary toilets etc;

- Rear (west) of existing A&E extended to accommodate psychiatric rooms.

Scheme benefits:

- Provides ED and UTC accommodation side by side with good connectivity.  Clinical team have advised that layout of resus, RAIT, Majors and Minors allows for good temporary compartmentation of areas from an operational perspective which would allow flexibility in use in the event of an infectious disease situation;

- Single point of entry with ED and UTC Triage and internal navigation hub for streaming;

- Large ambulance entrance lobby containing weighbridge and 5 trolley spaces, together with CBRN store;

- Bereavement suite provided, adjacent and above resus;

- Diagnostics suit available to both ED and UTC, located between the two for ease of access and containing both CT and X-Ray;

- Two room psychiatric suite achieved with separate entrance;

- Training and seminar accommodation provided, this at first floor level away from clinical areas.

- Staff changing, toilet and mess facilities at first floor level.   Additional local provision for staff toilets etc provided in both Resus / ED and UTC areas.

Scheme negatives compared with Option 4:

- frailty capacity reduced from 4 to 3 rooms;

- very little storage for ED stock – would need to find alternative space or reduce office space;

- existing staff from the H Block need to be accommodated in alternative space – plans include c1.2M for expansion of OP’s or portable buildings.

Option 5

Scheme characteristics:

- Remodelling of existing A&E to provide core ED spaces including 6 RIAT bays, 12 majors plus supporting services, entrance and triage spaces;

- Side (south) of existing A&E extended to accommodate 6 resus bays complete with donning and doffing rooms and supporting spaces.   This is a two-storey extension with plant being provided at first floor level;

- Rear (west) of existing A&E extended to accommodate diagnostic suite (but without CT) and a single psychiatric room.  This is a single storey extension;

- Front (east) of existing A&E extended to accommodate new baby change and infant feed areas.  This is a minor single storey extension;

- Existing support services block retained and reconfigured at ground floor level to provide main UTC spaces including Minors rooms, Fit-to-sit area, Clean Procedures, Plaster Room, FAU and Paeds suites.   Minor infill extensions added to provide the additional space required;

- Existing support services block reconfigured at first floor level to provide staff training and support areas together with AHU/ plant spaces as required to serve the ground floor accommodation below;   Minor infill extension added to north side to accommodate training facility.

Scheme benefits:

- Provides ED/A&E in existing location reusing existing building albeit extended;

- Provides UTC close to ED and again within an existing building;

- General increase in accommodation over that currently extant;

- New resus block has strong visual impact.

Scheme negatives compared with Option 4:

- Requires extensive road diversion to south of existing A&E to accommodate Resus block;

- Connectivity between ED and A&E is not as strong;

- Segregation of services does not work in the same fashion for easy temporary compartmentation;

- Smaller waiting space achieved, with less visual impact;

- No changing places / dignity suite provided;

- Navigation hub reduced in size;

- Resus facility has 6 dedicated bays but does not have the additional 3 resus capable bays located remotely within UTC to allow operation of resus if main resus block is infected;

- UTC minors / C/E rooms reduced in number from 15 to 10;

- 1no. housekeeping room omitted in UTC;

- 1no. fit-to-sit space lost in UTC (reduction 16 to 15);

- No bereavement suite provided to Resus;

- 1no. patient accessible WC lost in Resus area;

- Resus store omitted;

- GFL local staff facilities more remote;

- Reduced trolley space achieved at ambulance entrance;

- CT Scanner omitted;

- Psychiatric provision reduced by one room;

- FAU clean and dirty utility rooms omitted;

- Staff changing rooms reduced in area;

- Training rooms reduced in size;

- Existing staff from the H Block need to be accommodated in alternative space – plans include c1.2M for expansion of OP’s or portable buildings;

- Offices located further away from ED (though closer to UTC);

- General storage reduced from 184m2 to 42m2;

- Communication path between resus and ED requires staff to travel through UTC to reach it.

Option 8

Scheme characteristics:

- Remodelling of existing A&E to provide core ED spaces including 6 RIAT bays, 13 majors plus supporting services, navigation hub and some triage space;

- Front (east) of existing A&E extended to accommodate 6 resus bays complete with donning and doffing rooms and supporting spaces.  This is a two-storey extension with plant being provided at first floor level;

- Rear (west) of existing A&E extended to accommodate diagnostic suite (but without CT) and a single psychiatric room.  This is a single storey extension;

- Existing support services block retained and reconfigured at ground floor level to provide main UTC spaces including Minors rooms, Fit-to-sit area, Clean Procedures, Plaster Room, FAU and Paeds suites.  Minor infill extensions added to north and south sides to provide the additional space required;

- Existing support services block reconfigured at first floor level to provide staff training and support areas together with AHU/ plant spaces as required to serve the ground floor accommodation below;   Minor infill extension added to north side to accommodate training facility;

- Front (east) of support services block extended to provide new pedestrian entrance, waiting area, patient toilets and nappy change and baby feed areas.

Scheme benefits:

- Provides ED/A&E in existing location reusing existing building albeit extended;

- Provides UTC close to ED and again within an existing building;

- General increase in accommodation over that currently extant;

- New resus block and waiting areas extensions have strong visual impact.

Scheme negatives compared with Option 4:

- Connectivity between ED and A&E is not as strong;

- Segregation of services does not work in the same fashion for easy temporary compartmentation;

- No changing places / dignity suite provided;

- Navigation hub reduced in size;

- UTC minors / C/E rooms reduced in number from 15 to 10;

- 1no. patient accessible WC lost in FAU area;

- Clean and Dirty Utility facilities lost from FAU area;

- ED staff beverage facility omitted;

- 1no. patient accessible WC lost in ED area;

- UTC storage reduced in area;

- 1no. fit-to-sit space lost in UTC (reduction 16 to 15);

- Resus facility has 6 dedicated bays but does not have the additional 3 resus capable bays located remotely within UTC to allow operation of resus if main resus block is infected;

- No bereavement suite provided to Resus;

- GFL local staff facilities more remote;

- Reduced trolley space achieved at ambulance entrance;

- CT Scanner omitted;

- Psychiatric provision reduced by one room;

- Staff changing rooms reduced in area;

- Training rooms stores reduced in size;

- Offices located further away from ED (though closer to UTC);

- General storage reduced from 184m2 to 42m2;

- Communication path between resus and ED requires staff to travel through UTC to reach it;

- Very little storage for ED stock – would need to find alternative space or reduce office space;

- Existing staff from the H Block need to be accommodated in alternative space – plans include c1.2M for expansion of OP’s or portable buildings.

High Level Overview of Options:

This is a brief clinical overview and does not contain all of the issues such as reduction in clean / dirty utilities, WC’s, staff rooms etc.  Discussions continue with LPFT regarding provision of S136 areas, but their current strategy is to remove these from ED with dedicated facilities being opened on an adjacent site within the next 1-2 years.

Investment Appraisal

The full workings of the CIA model for the 4 options are available on request.

Note:

- Calculations for Optimism Bias were omitted from the model as per the instructions as this has been calculated at 24% for each option based on Green Book recommendations by the Trusts cost advisors in establishing the capital cost;

- The incremental costs within the following Economic Summary include revenue costs for building maintenance and equipment replacement at 10 years, over a 30 year building life, as well as the capital sum.

| Economic Summary (Discounted) - £'000 |  |  |  |  |
| --- | --- | --- | --- | --- |
|  | Option 4, PWF+ | Option 4a, PFW | Option 5, Do Less | Option 8, Do Min |
| Incremental costs - total | -£56,868.78 | -£44,626.06 | -£41,366.01 | -£38,611.28 |
| Incremental benefits - total | £65,176.26 | £57,873.04 | £21,878.49 | £14,326.21 |
| Risk-adjusted Net Present Social Value (NPSV) | £8,307.48 | £13,246.98 | -£19,487.52 | -£24,285.07 |
| Benefit-cost ratio | 1.15 | 1.30 | 0.53 | 0.37 |

The appraisal determined that Option 4a remains the best value for money solution with a societal benefit of £1.30 for every pound spent on the scheme over a 30-year life span.

Conclusion

Accepting that capital availability may place a constraint on the Trust, which may in turn lead to an option with less value for money, the Trusts preferred way forwards should be option 4a.

# Appendix F:  Planning

- Pre Approval / Advice Letter

- Planning Permission

# Appendix G:  National and Local Strategies

B.1	Transformation of Urgent and Emergency Care:  Models of Care and Measurement – December 2020

The Transformation of Urgent and Emergency Care: Models of Care and Measurement establishes a consultation on proposals that align care closer to the LTP.  This includes changes in the wake of the Covid-19 pandemic where attendances to ED fell and demand on 111 services increased due to the effect of the need for isolation and social distancing.  The report notes that numbers have now returned to near normal levels pre pandemic.

The paper details the outcome of a clinically led review of standards (CRS), as existing standards do not take into account acuity and patient safety and the changes to urgent care since the introduction of the 4 hour standard in 2004, including the introduction of specialist centres for stroke, development of UTC’s, NHS111, introduction of specialist trauma centres, cardiac centres and stroke units, etc.

The review, pending consultation, sets out the recommendations of the Urgent and Emergency Care workstream from the CRS, including:

- Booked appointments into ED and UTC’s;

- Capital to improve capacity and capability within the existing emergency departments;

- Increasing capital and capacity within 111 services and utilising technology more for Clinical Assessment Services such as video consultations;

- Minimising exit block from acute trusts;

- Promoting Same Day Emergency Care facilities.

The paper also puts forwards a number of possible new metrics for urgent care standards, including:

- Handover delays;

- Time to initial assessment;

- Mean time in the department for non-admitted patients;

- Percentage of patients spending more than 12 hours in the ED.

Whilst the paper talks about the need to reduce ED attendances by providing alternatives it also accepts that most ED’s do not have the required capacity to deal with new attendance levels and discusses the £450M the Government made available to 140 trusts to prepare for winter.  The investment is for rapid, immediate changes to emergency services to prevent nosocomial infection, improve flow through ED by increasing capacity and capabilities of the ED’s and UTC’s, provide priority admission units and expanding activity in SDEC.

B.2	Health Infrastructure Plan (HIP) – October 2019

The health infrastructure plan represents a long term investment in the NHS to develop capital projects.  This brought in additional funding to that announced within the NHS Long Term Plan, below.  The first wave of the HIP involves over 40 projects with the aim of delivery by 2025 and there will be future waves for other projects and schemes.

The plan outlines three key things to make the NHS Infrastructure fit for the future:

- A new five-year rolling programme of investment in NHS Infrastructure;

- A reformed system underpinning capital to ensure funding addresses need;

- Backing of wider health and care sectors with funding at the capital review.

B.3	NHS Long Term Plan – January 2019

The NHS Long Term Plan is a plan for the NHS to improve the quality of patient care and health outcomes. The plan focuses on building an NHS fit for the future by:

- Enabling everyone to get the best start in life;

- Helping communities to live well;

- Helping people to age well.

The plan was developed in partnership with frontline health and care staff, patients and their families.  It aims to improve outcomes for major diseases, including cancer, heart disease, stroke, respiratory disease and dementia.  The plan also includes measures to:

- Improve out-of-hospital care, supporting primary medical and community health services;

- Ensure all children get the best start in life by continuing to improve maternity safety including halving the number of stillbirths, maternal and neonatal deaths and serious brain injury by 2025;

- Support older people through more personalised care and stronger community and primary care services;

- Make digital health services a mainstream part of the NHS, so that patients in England will be able to access a digital GP offer.

To ensure that the NHS can achieve the ambitious improvements for patients over the next ten years, the NHS Long Term Plan also sets out how the NHS can overcome the challenges it faces, such as staff shortages and growing demand for services, by:

- Doing things differently:

- Give people more control over their own health and the care they receive;

- Encourage more collaboration between GPs, their teams and community services as ‘primary care networks’, to increase the services they can provide jointly;

- Increase the focus on NHS organisations working with their local partners, as ‘Integrated Care Systems’, to plan and deliver services which meet the needs of their communities.

- Preventing illness and tackling health inequalities:

- Increasing contributions to tackling some of the most significant causes of ill health, including new action to help people stop smoking, overcome drinking problems and avoid Type 2 diabetes, with a particular focus on the communities and groups of people most affected by these problems.

- Backing the NHS workforce:

- Continuing to increase the NHS workforce, training and recruiting more professionals – including thousands more clinical placements for undergraduate nurses, hundreds more medical school places, and more routes into the NHS such as apprenticeships;

- Developing new roles as described in the NHS Ten Year plan and the Primary Care Networks e.g. physicians associates, clinical pharmacists, social prescribers;

- Making the NHS a better place to work, so more staff stay in the NHS and feel able to make better use of their skills and experience for patients.

- Making better use of data and digital technology:

- Providing more convenient access to services and health information for patients, using the technology including GP on-line services and the new NHS App as a digital ‘front door’;

- Providing better access to digital tools and patient records for staff;

- Improve the planning and delivery of services based on the analysis of patient and population data.

- Getting the most out of taxpayers’ investment in the NHS:

- Continue working with doctors and other health professionals to identify ways to reduce duplication in how clinical services are delivered;

- Make better use of the NHS’ combined buying power to get commonly used products for cheaper;

- Reduce spend on administration.

A key focus of the NHS Long Term Plan is the need to incorporate effective use of technology to support the delivery of patient care in the future. In Lincolnshire, significant steps are already being taken including:

- Development and roll-out of the Lincolnshire Care Portal to provide health and care staff with integrated access to patient clinical information across different IT systems;

- The well-established Lincolnshire Clinical Assessment Service which runs alongside the NHS111 service and provides health information and advice to patients over the phone.

Going forwards, this work will be accelerated as a major component in delivery of the proposed new service models.

The design of any service at Pilgrim Hospital therefore needs to consider integration with local partners (LCHS, LPFT, EMAS, social care) and how technology can play a vital part in our services – educating patients as well as providing data on attendances and getting information back to GP’s about their patients care.

B.3	Five Year Forward View (October 2014)

The NHS Five Year Forward View, published in October 2014 by NHS England, set out a positive vision for the future based around seven new models of care:

Multispecialty community providers

Under this new care model GP practices come together in networks or federations and collaborate with other health and social care professionals to provide more integrated services outside of hospitals.

Urgent and emergency care networks

Under this new care model, the urgent and emergency care system should be simplified to provide better integration between Emergency Departments and other services that provide and support urgent treatments.

Specialised care

The NHS five year forward view outlined that, where there is strong evidence for concentrating care in specialist centres (as in stroke or some cancer services), the NHS in England should seek to drive consolidation through a programme of three-year rolling reviews.

Enhanced health in care homes

Under this new care model NHS services should work in partnership with care home providers and local authority services to develop new models of care and support for older people.

Primary and acute care systems

Under this new care model, a single entity or group of providers take responsibility for delivering the range of primary, community, mental health and hospital services for their local population, to improve co-ordination of services and move care out of hospital where appropriate.

Acute care collaborations

Acute care collaborations (ACCs) were announced as a new type of vanguard by NHS England and other national bodies in September 2015. ACCs aim to link together hospital services to improve care quality and financial sustainability.

Modern maternity services

The NHS five year forward view proposed a new care model for modern maternity services, stating that a review of future models for maternity units would recommend how best to sustain and develop maternity units across the NHS in England.

As with the long term plan, integration of the emergency department with other providers in an “Integrated Care Network” is pivotal in the design of Pilgrim Hospitals services.  With the current service there is an entrance to the emergency department as well as an entrance in Primary Care Streaming which creates confusion.  A single entrance with service providers working together with referral pathways into the “majors” and “resus” areas and “minors” patients being seen alongside primary care work within the UTC area will remove any decisions patients have to make about where to go to receive care.

Pharmacy provision at Pilgrim Hospital is also an issue, being located towards the back of the hospital in a space insufficient for the workload.  The community element is co-located with the hospital pharmacy but by moving this to the front door more patients that would otherwise attend ED could self-care and receive advice without attending.  This would also release much needed space for the existing hospital pharmacy services.

B.4	Next Steps on the NHS Five Year Forward View (March 2017)

This delivery plan, drafted by both NHS Improvement (NHSI) and NHS England (NHSE), outlined progress on the ambitions set out in the Five year forward view since its original publication in October 2014, and defined what still needed to be achieved over the final two years of the plan. It also outlined priorities for the service specifically in 2017/18 as follows:

- Deliver financial balance across the NHS;

- Improve ED performance;

- Strengthen access to GP & primary care services;

- Improve cancer and mental health services.

Specifically, the plan sought to strike a balance between realism about the challenges facing the NHS today together with promises to improve care. These promises focussed on urgent and emergency care, primary care, cancer, and mental health.  They included delivering the four hours standard in all emergency departments during 2018, providing extended access to general practice appointments in the evenings and weekends in all areas of the country by March 2019, introducing a new standard to give patients a definitive cancer diagnosis within 28 days after GP referral by 2020, and increasing the availability of psychological therapies and mental health services for children and young people.

The ‘Next Steps’ also set out that one of the key ways for the achievement of longer term transformational change, would be to:

‘Encourage practices to work together in ‘hubs’ or networks.  Most GP surgeries will increasingly work together in primary care networks or hubs.  This is because a combined patient population of at least 30,000-50,000 allows practices to share community nursing, mental health, and clinical pharmacy teams, expand diagnostic facilities, and pool responsibility for urgent care and extended access.  There are various approaches to achieving this that are now being introduced across England, including federations of practices, ‘super-surgeries’, primary care homes, and ‘multispecialty community providers’.

Extended access to GP and primary care services has been established in the Boston area for some time.  However, the service is intermittent and bringing it into the UTC with collocated services will help to create more consistent provision.

B.5	General Practice: Forward View (April 2016)

The General Practice Forward View, published in April 2016, set out a plan, backed by significant national investment, to stabilise and transform general practice.  It was developed with Health Education England and in discussion with the Royal College of GPs and other GP representatives.

It committed to an extra £2.4 billion a year to support general practice services by 2020/21, supplemented by a five-year national sustainability and transformation package to support GP practices.  The plan also contained specific, practical and funded steps to grow and develop workforce, drive efficiencies in workload and relieve demand, modernise infrastructure and technology, and support local practices to redesign the way modern primary care is offered to patients.

B.6	Urgent Treatment Centres

Urgent Treatment Centres - Principles and Standards was published in July 2017 to support simplification of the urgent and emergency care system and to provide better integration between Emergency Departments and other services that provide and support urgent treatments.  The document provided a specification for UTCs to establish as much commonality as possible, setting out a series of clear expectations as follows.

By December 2019 patients and the public will:

- Be able to access urgent treatment centres that are open at least 12 hours a day, GP-led, staffed by GPs, nurses and other clinicians, with access to simple diagnostics, e.g. urinalysis, ECG and in some cases X-ray;

- Have a consistent route to access urgent appointments offered within 4hrs and booked through NHS 111, ambulance services and general practice. A walk-in access option will also be retained;

- Increasingly be able to access routine and same-day appointments, and out-of-hours general practice, for both urgent and routine appointments, at the same facility, where geographically appropriate;

- Know that the urgent treatment centre is part of locally integrated urgent and emergency care services working in conjunction with the ambulance service, NHS111, local GPs, hospital Emergency Departments and other local providers.

The expectation is that this change will create the opportunity for the commissioning of a genuine integrated urgent care service, aligning NHS 111, urgent treatment centres, GP out-of-hours and routine and urgent GP appointments with face to face urgent care.

This represents a national drive to provide a simplified networked model of urgent care services presented to the public using a standardised nomenclature.  As such, MIUs are likely to translate into newly-specified primary care access hubs following local consultation and engagement.

Urgent treatment centres are expected to operate as part of a networked model of urgent care, with referral pathways into emergency departments and specialist services as required.  Commissioners are expected to make sure that all UTC services form part of ambulance services referral pathways as an alternative to conveyance to the ED where appropriate.

This key publication established a blueprint for the design of the UTC at Pilgrim Hospital.  Patients must have access to routine, same day and urgent (within 4 hours) primary care services both in and out of core hours.  The service must have seamless integration – patients will be almost unaware of which organisation is providing their care with the ED and UTC being completely integrated.

B.7	The Carter Report

Lord Carter’s interim report in June 2015 and February 2016 (Operational productivity and performance in English NHS acute hospitals: Unwarranted variations) outlined the work that has been carried out to review the operational productivity of NHS hospitals, working with a group of 22 NHS providers.  The report provided interim recommendations and next steps for efficiency centred on workflow, workforce, pharmacy and medicines optimisation and estates and procurement management.

A key interim recommendation was the need for a common set of metrics that could serve as a barometer for hospitals to compare themselves with their peers, taking into account the complexity of care provided, and more importantly provide a baseline for future improvement.  This would enable hospital leaders to pinpoint areas of improvement and identify where large improvements could be made by reducing variation in services.

Lord Carter’s final report published in February 2016 identified significant and unwarranted variation in costs and practice which, if addressed, could save the NHS £5bn.  The report acknowledges that although there is exceptional practice already happening in the NHS, the overall average is not sufficient and more needs to be done to bring poor performance up to meet the best.  It concluded there is the potential for efficiency savings of £1bn from better management of estates, such as lighting, heating and utilising floor space, with a large variation between Trusts, with one using just 12% for non-clinical purposes, while another used over two-thirds.  The report recommended that:

- “Every Trust has a strategic estates and facilities plan in place, including in the short term, a cost reduction plan based on the model hospital data and benchmarks, and in the longer term a plan for investment and reconfiguration where appropriate for their whole estate, taking into account the Trust’s future service requirements”;

- “All Trust’s estates and facilities departments should operate at or above the median benchmarks for the operational management of their estates and facilities functions (as set by NHS Improvement by April 2016); with all Trusts (where appropriate) having a plan to operate with a maximum of 35% of non-clinical floor space and 2.5% of unoccupied or under-used space by April 2017 and delivering this benchmark by April 2020, so that estates and facilities resources are used in a cost effective manner.”

This OBC responds to the Carter report by proposing to maximise the amount of clinical space in relation to the ED at the Pilgrim Hospital, Boston.  Also, by addressing the current capacity issues, it is proposed to enable provision of an efficient urgent care service for the east Lincolnshire area, therefore improving cost effectiveness.

B.8	NHS Property and Estates: Why the estate matters for patients (March 2017)

The NHS Property and Estates review (an independent report by Sir Robert Naylor) presented the opportunity to rebuild NHS infrastructure to meet modern standards of service delivery for the future and calls for the NHS, through the STP process to rapidly develop robust capital plans that are aligned with clinical strategies, maximise value for money (including land sales) and address backlog maintenance.  This project responds to the Naylor Review by making more intensive use of the existing estate and maximising and improving clinical standards and functional suitability.

B.9	Local Estates Strategies (DoH June 2015)

Achieving the efficiencies required by the Five Year Forward View requires all parts of the health service to work with greater agility and co-operation. Good quality strategic estates planning is vital to making the most of these changes and will allow the NHS to:

- Fully rationalise its estate;

- Maximise use of facilities;

- Deliver value for money; and

- Enhance patients’ experiences.

In order to realise these benefits, commissioners, trusts and stakeholders (including the wider public estate) were required to produce local estates strategies.  The formation of Local Estates Forums (LEF) has been key to developing a sufficiently robust understanding of the available estate and aligning it to commissioning intentions to extract maximum value from NHS resources and reduce wastage.

It is critical that service and estates planning are integrated to ensure that the best estate is available to deliver optimised healthcare services and facilitate wisely, well-founded investment decisions.  In this way, best use can be made of existing property, new estate can be developed to meet service needs and surplus estate can be sold.

B.10	Estates and Technology Transformation Fund

NHS England’s Estates and Technology Transformation Fund (ETTF) is a multi-million pound investment (revenue and capital funding) in general practice facilities and technology across England (between 2015/16 and 2019/20). It is part of the General Practice Forward View commitment for more modernised buildings and better use of technology to help improve general practices services for patients.

The ETTF funding comes out of the £1bn Primary Care Infrastructure Fund which as well as providing a funding boost for estates and technology has invested in other areas of general practice such as workforce.

B11	Lincolnshire STP Estates Strategy

The draft Lincolnshire STP Estates Strategy was released in July 2018.  It describes a strong commitment to organisations within the health system working together with a common purpose, to continue to raise standards and to ensure we deliver the best possible outcomes for the people of Lincolnshire.

It notes that some of our patients and staff are in buildings not fit for the demands of todays health care.  It describes the extreme issues at both Pilgrim and Lincoln County Hospitals regarding A&E performance and capacity and the need to reconfigure a number of specialities including acute care across the system.  The plans to reconfigure the ED at Pilgrim Hospital are in line with this strategy.

B.12	ULHT Estates Strategy

This scheme fits within the estates strategy in terms of its potential to reduce backlog maintenance and investing in the clinical estate.  It will help the trust to deliver a flexible, high efficiency estate with a functionally fit for purpose, future proofed building.  The design will be flexible for future clinical needs.  As it is often perceived as the “gateway to the site” it will be a landmark building from a design quality and wayfinding perspective, providing a direct visual link to patients and service users upon entering the site.

The development control plan shows the site and the building marked “1” as the H Block, which indicated it for demolition.  Please see appendix H for the full strategy.

B.13	ULHT Clinical Strategy

The wider NHS is experiencing unprecedented change.  It is becoming a system that is highly regulated by external bodies such as the Care Quality Commission (CQC) and NHS England and Improvement.  National standards are set and some of these will be mandatory with the further development of NICE quality standards.  Specialised care is becoming more complex within an environment where increasing demand and public expectations mean that care will be delivered closer to the individuals’ own home, with an integrated workforce.  ‘Integration’ meaning that the workforce from ULHT, Lincolnshire Community Health Services, Lincolnshire Partnership Foundation Trust and primary care will come together to provide care as integrated teams to support patients closer to home, and avoid unnecessary admissions to acute hospitals.  All these changes are required within a constrained financial resource.

The United Lincolnshire Hospitals Clinical Strategy was developed to address these changes and outlines the direction of travel of ULHT services.  It has been developed to ensure that the organisation is clear about its role in providing secondary healthcare in the future.

After some challenging times, ULHT is on a journey of improvement with patient safety and improving the patient experience being the highest priorities.  However, ULHT is part of a broader healthcare system and the changing external environment and expectations of partner organisation need to be addressed in this strategy and as such, the developed Clinical Strategy takes into account the working of both Lincolnshire’s Sustainability and Transformation Programme (STP) and the Acute Services Review (ASR).

Developing this strategy has identified the following key points:

- Services are not clinically sustainable in the current configuration;

- Services are not affordable in the current configuration;

- Doing nothing is not an option;

- Services need to be better integrated and coordinated to deliver an improved patient experience and outcome closer to home;

- Care needs to be consultant-led 24/7;

- There is a balance to strike between the need to concentrate scarce specialist resources and ensure local access;

- In-hospital services need to be fully utilised to achieve maximum economies of scale;

- Telemedicine technologies need to be used to the maximum in Lincolnshire to minimise the problems associated with rurality.

The trusts Integrated Improvement Plan 2020-2025 builds on this strategy setting out the need for staff to work differently, integrating services supported by technology in an improved estate within its core strategic objectives.  This OBC will consider the integration of services and how this can be underpinned by better technology.

# Appendix H:  ULHT Estates Strategy

Already within the public domain.

United Lincolnshire Hospitals NHS Trust Estates Strategy 2022

# Appendix I:  Cabinet Office Risk Potential Assessment

| 1. Policy, programme or project name (Also note previous name if it has changed since last assurance review) | Project to Develop Resuscitation Facilities, Implement a New Urgent Treatment Centre and Reconfigured Emergency Department at Pilgrim Hospital, Boston. |
| --- | --- |
| 2. Change driver (Primary reason for change) | Ministerial initiative* Legal* Operational Business Change* Other *(provide short explanation) * delete as appropriate |
| 3. Programme/project type | 1. Government Transformation & Service Delivery* 2. ICT* 3. Infrastructure & Construction* 4. MoD Capability* *delete as appropriate |
| 4. Objectives and expected benefits | Cash Releasing Benefits: Reduced Conversion Rates and Length of Stay Energy Efficiency Fit with Travel Plans Potential Income from ED Clinics Pharmacy Income / Rent Possible Emergency Dentistry Services Oversees Visitor Income Non Case Releasing: Shared, more resilient workforce Quantifiable Benefits: Patient Outcomes Improved recruitment Staff satisfaction Qualitative Benefits: Better access Improved patient satisfaction Productivity |
| 5. Department, Agency, or NDPB name & parent department name (if applicable) | Name: Emergency Department, Pilgrim Hospital Boston Parent Dept: Division of Medicine, United Lincolnshire Hospitals |
| 6. Contact Details: Senior Policy Owner (SPO) (for Starting Gate) Senior Responsible Officer (SRO) (for existing project or programme) | Name: Mark Brassington, Chief Operating Officer Address: Lincoln County Hospital, Greetwell Road, Lincoln LN2 5QY Telephone No. 01522 573013 Email: mark.brassington@ulh.nhs.uk |
| 7. Programme Director details | Name: Andrew Prydderch, Deputy Director of Operations Address: Lincoln County Hospital, Greetwell Road, Lincoln LN2 5QY Telephone No. 01522 573305 Email: andrew.prydderch@ulh.nhs.uk |
| 8. Primary contact point for administration of assurance reviews | Name: Andrew Prydderch, Deputy Director of Operations Address: Lincoln County Hospital, Greetwell Road, Lincoln LN2 5QY Telephone No. 01522 573305 Email: andrew.prydderch@ulh.nhs.uk |
| 9. If a programme, please list names of the constituent projects. If a project, please give name of the over - arching programme. | Lincolnshire Urgent and Emergency Care Delivery |
| 10. Costs (Indicative estimate or as defined in latest business case) | Capital: £36.8M Operational (Running costs): £0.3M Whole life: £ Business Case Status: Submitted OBC |
| 11. Expected duration (yrs) of major contract or service (if known & appropriate) |  |
| 12. Next planned review | Project Validation Review (PVR) * Project Assessment Review (PAR) * Gate 0, 1, 2, 3, 4, 5 * * delete as appropriate |
| 13. Requested start date for next review (This should be approximately 12 weeks after the Assessment meeting) | Week Commencing Date: |
| 14. Overall Assessment Derived from Table C | Low/Medium/High* HIGH * delete as appropriate |
| 15. Date of previous assurance review & IPA ID No. | Type of Review: Date: ID No. |
| 16. Name of responsible Minister |  |
| 17. RPA approved by SRO (or could be Senior Policy Owner if for a PVR) | Name: Date: |
| 18. Validated by organisation’s Portfolio Manager or an equivalent e.g. Head of PPM Centre of Excellence | Name: Date: Role: Email: Tel. No. |
| 19. Departmental Assurance Co-ordinator (DAC) | Name: |
| 20. RPA Version No. & Date | Version No. Date: |
| The General Data Protection Regulation and Data Protection Act 2018 It is intended that the data collected via this form will be used by the Cabinet Office for its own purposes and also to inform other areas of Government business. The data may also be used to make you aware of services, advice and guidance. Issues related to the use of personal data within this form should be addressed to: Gateway.Helpdesk@ipa.gov.uk |  |

| Table A Consequential Impact Assessment A strategic assessment of the consequential impact should the initiative fail to deliver its objectives to time, cost or quality |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Strategic Impact Area |  | Very Low | Low | Med | High | Very High |  |
| A1. Political | None, or unlikely to have any political interest. |  |  |  |  | X | As a prerequisite for major policy initiative or manifesto commitment, a high level of on-going Ministerial or political interest. Likelihood of PAC, or equivalent strategic body, interest. |
| Explanatory Notes (Completion mandatory) | Scored VH due to a high level of on-going Ministerial or political interest. Announcement for funding for organisations was made by the Prime Minister in person at Pilgrim Hospital. |  |  |  |  |  |  |
| A2. Public | No public service impact. No information security or environmental implications. No interest from external pressure groups likely. |  |  |  | X |  | Significant public or business interest, e.g. related to information security, or to environmental issues. High degree of interest from pressure groups or media. Involves contentious change. |
| Explanatory Notes (Completion mandatory) | Due to a high level of media involvement from the outset of the project as well as an already motivated population in the surrounding area this scheme will attract a high level of public interest. |  |  |  |  |  |  |
| A3. Financial | Little or no exposure of public funds or additional financial burden. No financial impact from environment or social costs. Limited or no savings to be delivered. |  |  |  | X |  | Very significant financial exposure of public funds, or additional financial burden. Significant financial impact from environmental or social change. Will, or likely to, require HM Treasury financial approval. Very significant savings expected to be delivered. |
| Explanatory Notes (Completion mandatory) | High value (36.8M) scheme that will require approval from NHSE and HMT. Potential to deliver some savings although main driver will be improvement in patient care. |  |  |  |  |  |  |
| A4. Operational business and commercial change | Low priority, limited impact on the organisation’s administration, operations or staff. No impact on third party organisations. No changes to regulatory requirements. |  |  |  |  | X | Departmental priority, addressing high profile business issue. Essential to fulfil legislative/legal requirements. Significant impact or additional burden on business or staff, on external commercial markets, regulations or trade. The change is novel or contentious. |
| Explanatory Notes (Completion mandatory) | The project is critical to delivery of urgent care on the site and thus an extremely high priority. It will cause a significant impact and burden on staff during the building work and will represent a completely different way of working with integration of 2 separate trusts. |  |  |  |  |  |  |
| A5. Dependencies | Stand alone - no dependency either way on other initiatives, programmes or projects. |  |  | X |  |  | Highly dependent on other legislation, programmes, projects or change initiatives for its successful delivery, and/or vice versa. |
| Explanatory Notes (Completion mandatory) | NHSE requirement to have UTC’s on all acute A&E sites by December 2019. However, some organisations have integrated this into the existing A&E and not had a separate department which seems to have worked better. A&E at PHB does not perform well so this development will be of benefit to patients and fits within the overarching urgent care delivery programme. |  |  |  |  |  |  |
| Overall Consequential Impact Assessment |  |  |  |  |  |  |  |
| A6. Little or no impact on the public, political stakeholders, public finances, operational business or dependent programmes/projects |  | VL | L | M | H X | VH | Very high impact on the public, political stakeholders, public finances, operational business or dependent programmes/projects |
| Explanatory Notes (Completion Mandatory) The risk of not completing this project will mean that urgent care standards are not met and patient care is of poor quality in terms of infrastructure and capacity. Politically this is a very high profile and failure would almost certainly attract political and public attention. |  |  |  |  |  |  |  |

| Table B Programme/Project Complexity Assessment An assessment of the complexity factors that may affect the achievement of the programme/project objectives |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B1Strategic Profile |  | Very Low | Low | Med | High | Very High |  |
| B1.1. Political | No political involvement or does not require any special handling or additional engagement. |  |  |  | X |  | Multiple political interests requiring handling. Political agenda changing, unclear direction or increasing opposition. External political interests involved. |
| Explanatory Notes | The project reports into the leading organisations trust board and some subcommittee’s but also into the system urgent care board and executive teams. It is also part of political drives to increase spending on the NHS and reports into NHSE/I. |  |  |  |  |  |  |
| B1.2. Public | No or very low public profile. No change in public interest or service provision. No interest from external pressure groups. |  |  |  | X |  | Very high public profile, significant interest from public and/or from active pressure groups/media. Complex external communications. |
| Explanatory Notes | There is public and communications involvement on the project groups and significant interest from local media. The initial announcement of funding for NHS organisations was made at PHB and so attracted national media attention. The project will have to deal with numerous enquiries throughout its life. |  |  |  |  |  |  |
| B1.3. Business performance | No significant change to the organisation’s business. No change to the operation of external bodies. |  |  |  |  | X | Very high business performance profile. Changing demands or expectations of performance or staff or behaviours. Significant changes to consumer or business operations. |
| Explanatory Notes | Complex contractual changes to staff working in the delivery of urgent care. New patient pathways significantly changing the way A&E works. Careful consideration of how these changes will be implemented without any change in expectation from patients. |  |  |  |  |  |  |
| B1.4. Organisational objectives | No links to strategic targets or published performance indicators. Strategic status (portfolio position), mandate and objectives clear, stable and unlikely to change. |  |  |  | X |  | Critical link to delivery of key strategic objectives and/or published targets. Strategic status, mandate or objectives likely to change. |
| Explanatory Notes | Directly linked to the organisations performance against constitutional standards. Objectives and mandate are, however, unlikely to change. |  |  |  |  |  |  |
| Strategic Profile summary assessment | Strategic profile low, changes unlikely to threaten objectives | VL | L | M | H X | VH | Strategic profile very high and changes highly likely to threaten achievement of objectives |
| Explanatory Notes (Completion Mandatory) This is a complex project involving disruption to existing services and phasing construction. It has a great deal of political and media interest that will have to be handled carefully throughout. Success is imperative due to the impact on constitutional standards and the quality of care which the organisation needs to improve as a priority. [Note: Record summary assessment mark to Complexity Assessment Summary table below] |  |  |  |  |  |  |  |

| Table B Programme/Project Complexity Assessment An assessment of the complexity factors that may affect the achievement of the programme/project objectives |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| B2 Delivery Challenge |  | Very Low |  | Low | Med | High | Very High |  |
| B2.1. Policy/Legal | No legal matters or legislation involved. Policy and legal implications fully understood, aligned and stable. Policy development assurance review (e.g. PVR or equivalent) undertaken. |  |  |  | X |  |  | Affects complex, multiple or cross-border jurisdictions. Legal, legislative or cross organisational policy unclear or changes and challenges highly likely. No policy development reviews undertaken. |
| Explanatory Notes | Multiple agency project but not anticipated to have legal or legislative impact. |  |  |  |  |  |  |  |
| B2.2. Security | No security or public data handling implications. |  |  | X |  |  |  | Significant national security or public data handling issues or requirements. |
| Explanatory Notes | No additional security or data handling implications other than those already in place. |  |  |  |  |  |  |  |
| B2.3. Requirements for business change | Stable business, no significant changes envisaged to requirements. Implications established of wider strategic changes, e.g. green agendas, sustainability. Clearly defined, agreed measurable outcomes. Limited change to business operations. |  |  | X |  |  |  | Multiple, interdependent and complex requirements that are dependent on wider emerging or change initiatives e.g. sustainability. Extensive change to business operations or additional information reporting requirements. Significant unplanned changes to business requirements or outcomes likely to be imposed or required. |
| Explanatory Notes | Significant planned changes to business requirements. Ultimately little change to services from a patient perspective. |  |  |  |  |  |  |  |
| B2.4.Technology development, production and/or techniques | Involves no new or novel technology development, implementation, production, products, tools or techniques. Extensive previous use of development and/or production techniques. |  |  |  |  | X |  | First or extensive use of leading edge, novel or innovative technology. High degree of design, build or implementation complexity or uncertainty. Technology or methodology likely to be subject to major changes. |
| Explanatory Notes | New build project which will implement new design ideas to improve urgent care services. Some issue with multiple agencies using different IT systems – separate subgroup to look at new IT solutions. |  |  |  |  |  |  |  |
| B2.5. Commercial and supplier delivery | Established contracts or existing frameworks to be used. Commercial environment stable. Experienced sector suppliers. Single supplier or short supply chain. |  |  |  |  | X |  | Complex or innovative commercial arrangements. Supplier market limited and/or very specialist. Multiple suppliers or complex/volatile supply or logistical chain. |
| Explanatory Notes | Likely that the project will use existing procurement routes although the trust is considering bringing more work in house to reduce cost. No anticipated supplier issues although some uncertainty over suppliers ability to deliver raw materials post “Brexit” remains. |  |  |  |  |  |  |  |
| B2.6. Financial provision | Funding from within organisation budgets, no influence from economic climate. Supplier’s funding all in place. |  |  |  |  | X |  | Complex cross-organisational funding arrangements. Funding not agreed or in place. Third party or supplier funding not in place. Economic conditions likely to affect funding options or availability. |
| Explanatory Notes | Funding via NHSE agreed on delivery of successful FBC passing NHSE and HMT assessment. No early fees currently agreed to develop the project through OBC and FBC. |  |  |  |  |  |  |  |
| B2.7. Governance and programme/project management | Straightforward and stable governance structure. Recognised formal PPM methodologies in use. Key post holders in place. |  | X |  |  |  |  | Complex or multi-faceted governance or management structures. Governance, management structures or key post holders likely to change. |
| Explanatory Notes | Formal governance structures established with oversight group chaired by COO as SRO. No anticipated changes to post holders or structure. |  |  |  |  |  |  |  |
| B2.8. Stakeholders | Single stakeholder community, fully bought-in. No expected change in stakeholder environment or from agreed requirements and outcomes. |  |  |  | X |  |  | Complex stakeholder community. Stakeholder environment volatile or with significant external change factors. |
| Explanatory Notes | Multiple stakeholders involved but within a stable environment with recognised business needs. |  |  |  |  |  |  |  |
| B2.9 Dependencies | Stand alone, no or few dependencies on or for other programmes or projects. All statutory approvals or authorisations in place. |  |  |  |  | X |  | Complex dependency relationships with other initiatives or organisations. Significant external statutory authorisations or approvals (e.g. legislation, financial approvals, planning consent etc) remain outstanding or require explicit management. Dependencies changing or conflicting and/or coordination increasingly challenging. |
| Explanatory Notes | External financial approvals required from NHSE and HMT. Planning consent will be required due to new build element. |  |  |  |  |  |  |  |
| B2.10. Change and implementation | Single or co-located programme/project and supplier teams; single site delivery. No conflicting internal business change issues to affect change. Simple acceptance and cut-over issues. No “big bang” delivery. Change and benefits management fully embedded. |  | X |  |  |  |  | Complex national or international delivery environment. Changing or uncertain implementation, cultural or physical challenges to changes likely or expected. Big bang implementation. Complex testing and cut-over issues. |
| Explanatory Notes | Phased implementation of a co-located single site project. |  |  |  |  |  |  |  |
| Delivery Challenge summary assessment | Challenges to deliver are very low and change is unlikely to threaten objectives | VL | L |  | M X | H | VH | Very high degree of challenge and changes are highly likely to threaten achievement of objectives |
| Explanatory Notes (Completion Mandatory) Some complexities from multiagency project and requiring external approvals. However, it is felt the project can be, to a large extent, worked up internal with only moderate risk to ability to deliver. [Note: Record summary assessment mark to Complexity Assessment Summary table below] |  |  |  |  |  |  |  |  |

| Table B Programme/Project Complexity Assessment An assessment of the complexity factors that may affect the achievement of the programme/project objectives |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B3 Capacity and Capability |  | Very Low | Low | Med | High | Very High |  |
| B3.1. Programme or project team | Fully resourced and skilled team. Stable team, no recruitment issues. Specialist support (e.g. commercial, legal) in place or available when required. Experienced with similar change or technology projects. |  |  |  | X |  | Personnel resources or funding not available when required. Significant resource changes likely leading to skill gaps or disruption to key posts. No previous experience with similar change or technology. |
| Explanatory Notes | Key issue around approvals for funding, potential approval delays and limited early release to develop to the project. Project team in place with some experience to deliver the project but some recognised gaps being managed. |  |  |  |  |  |  |
| B3.2 Stakeholders and organisation | Fully resourced and skilled, available when required. Open to and comply with change. Common and accepted priority across an engaged stakeholder community. | X |  |  |  |  | Key resources or skills lacking or unavailable when required. Changing environment. Business priority is low, inconsistent or changing. Significantly differing priorities between stakeholder groups. |
| Explanatory Notes | Most stakeholders on board with the scheme with clear and unified goals. |  |  |  |  |  |  |
| B3.3. Suppliers (internal or external) | Experienced, strong and stable market or suppliers. Supplier resources skilled and available, with ongoing support and commitment. |  | X |  |  |  | No, weak or overstretched market - unlikely to meet demand. Suppliers unable to sustain support, withdraw, or cannot meet requirements. |
| Explanatory Notes | The trust has a lot of experience working with local contractors on several large capital projects. |  |  |  |  |  |  |
| B3.4. Strategic leadership and business culture | Good capacity, continuity and experience in leadership roles. No unforeseen organisational pressures. Open culture for change, no staff or trade union concerns. |  |  | X |  |  | Strategic leadership subject to change. No previous responsibility for or direct experience of change of similar magnitude or complexity. A challenging cultural, staff or workload environment. |
| Explanatory Notes | High pressure working environment due to existing constraints on urgent care, however, no anticipated changes to continuity in leadership roles. |  |  |  |  |  |  |
| Capacity & Capability summary assessment | Capacity and capability in place and change unlikely to threaten objectives | VL | L X | M | H | VH | Significant capacity or capability issues. Changes highly likely to threaten achievement of objectives |
| Explanatory Notes (Completion Mandatory) No major complexity issues identified that could affect the ability to achieve the project. The organisations have sufficient capacity to deliver but require assistance in terms of early release of funding to develop the scheme. [Note: Record summary assessment mark to Complexity Assessment Summary table below] |  |  |  |  |  |  |  |

| Table B Programme/Project Complexity Assessment An assessment of the complexity factors that may affect the achievement of the programme/project objectives |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
| B4 Scale |  | Very Low | Low | Med | High | Very High |  |
| B4.1 Time | Timescales not challenging, no external drivers. No imposed changes expected to the agreed schedules. Contingency available and tested business continuity plans. |  |  |  |  | X | Schedules very challenging. Immovable deadlines. Major changes to deadlines or imposed deadlines likely to occur. Very limited or no contingency or contingency options available. |
| Explanatory Notes | High pressure to deliver quickly due to political pressure and the need to reform urgent care may lead to significant constraints and unknown issues throughout the project. |  |  |  |  |  |  |
| B4.2 Budget | Budgets within delegations and local control. Costs relatively small to overall organisational portfolio spend. Budgets agreed and stable. Appropriate financial management systems established. Change management system in place. |  |  | X |  |  | Budgets outside organisational spend delegations. Cost estimates subject to significant pressures from ongoing or expected change. Costs are significant, relative to the organisation’s programme/project spend. Financial management system not in place or audited. Cross organisational/ multi-faceted funding with complex financial control and reporting. |
| Explanatory Notes | Significant capital requirement. Budget is largely outside of the organisations control although an agreed envelope based on the SOC’s has been approved. Costs are now very significant and in excess of the original agreement. |  |  |  |  |  |  |
| B4.3 Benefits | Benefits relatively small. Benefits easily and clearly defined, owned, measurable and achievable. No expected changes which might increase scale of benefits. |  |  |  | X |  | Magnitude of benefits significant. Complex benefits realisation challenges. Changing benefits management environment or realisation responsibilities. Achievability of benefits in doubt. Difficult to measure. |
| Explanatory Notes | Potentially large benefits to performance and quality of care, however investment needed across the whole hospital as flow out of the site impacts on the ability of A&E to deliver. This may reduce the performance benefits although improvements to dignity and quality of care should remain. |  |  |  |  |  |  |
| B4.4. Quality | Quality requirements clear, easily achievable and stable. |  |  |  | X |  | Quality targets extremely challenging, likely to change significantly, or hard to achieve. |
| Explanatory Notes | Constitutional standards will still be at risk as described above. |  |  |  |  |  |  |
| Scale summary assessment | Small scale, changes unlikely to threaten objectives | VL | L | M | H X | VH | Very large scale, and changes highly likely to threaten achievement of objectives |
| Explanatory Notes (Completion Mandatory) Difficult timeframe, fixed budget and potential impact on benefits without investment in the whole patient pathway will increase the risk to achieving the benefits in the project. [Note: Record summary assessment mark to Complexity Assessment Summary table below] |  |  |  |  |  |  |  |

| Complexity Assessment Summary (Insert the marks allocated for each of the four (yellow) summary assessments from Table B above) |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Complexity Areas summary assessments | VL | L | M | H | VH |
| Strategic Profile (B1.1 – B1.4) |  |  |  | X |  |
| Delivery Challenge (B2.1 – B2.10) |  |  | X |  |  |
| Capacity and Capability (B3.1 – B3.4) |  | X |  |  |  |
| Scale (B4.1 – B4.4) |  |  |  | X |  |
| B5. Overall Complexity Assessment |  |  |  | X |  |
| Explanatory Notes (Completion Mandatory) High profile project with political and public interest working within a finite budget and fast timeframe. Whilst the organisations have capacity to deliver, external factors such as availability of funding are a key constraint which place the project at higher risk. [Note: assessment above to be used on Table C] |  |  |  |  |  |

| Table C Risk Potential Assessment Plot overall summary assessments from Table A (line A6) and Table B (line B5) and mark with an X in grid below |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Overall Consequential Impact Assessment (Table A summary) | Very High |  |  |  | High Risk |  |
|  | High | Medium Risk |  |  | X |  |
|  | Medium |  |  |  |  |  |
|  | Low |  |  |  |  |  |
|  | Very Low |  |  | Low Risk |  |  |
|  |  | Very Low | Low | Medium | High | Very High |
| Overall Complexity Assessment (Table B summary) |  |  |  |  |  |  |
| Now transfer the Risk Potential Assessment score from Table C to Box 14 on the cover sheet of this form. |  |  |  |  |  |  |
| Please send the fully completed and approved RPA to your Departmental Assurance Coordinator (or equivalent), who will pass it on to your organisation’s Portfolio Manager (or equivalent) for validation. Who arranges the review? In central government the “arrange and manage” process for Project Validation Reviews, OGC Gateway™ and Project Assessment Reviews is generally as follows: Major Projects & High Risk Assurance Reviews: By the IPA Medium Risk Assurance Reviews: By Departments, under delegation from the IPA Low Risk Assurance Reviews: By Departments, usually through consultation with their DAC/Centre of Excellence (or equivalent). All RPAs indicating a requirement for Medium or High Risk reviews will be checked at the Assessment meeting. Scheduling and lead time: When planning an assurance review, please assume 12 weeks from the date of the Assessment meeting to the start of the review, not from the date when the RPA was submitted. PLEASE NOTE: It may not be possible for the IPA to arrange a review at short notice as reviewers’ availability may be limited. Failure to provide sufficient information in this RPA may delay the timing of your assurance review. DAC submission of RPA: Please delete the user guidance pages, and ensure the security classification is correct, before sending the completed RPA to gateway.helpdesk@ipa.gov.uk |  |  |  |  |  |  |

© Crown Copyright 2016

Produced by the Infrastructure and Projects Authority

You may re-use this document template (excluding logos and trademarks) free of charge in any format or medium, under the terms of the Open Government Licence.

To view this licence, visit:

http://www.nationalarchives.gov.uk/doc/open-government-licence/ or e-mail: psi@nationalarchives.gsi.gov.uk

Where we have identified any third party copyright information, you will need to obtain permission from the copyright holders concerned.

Further Information

If you have any further questions about the use or completion of this template, please first contact your organisation’s Departmental Assurance Coordinator (or equivalent), or the IPA via Gateway.Helpdesk@ipa.gov.uk

This document is available on the assurance toolkit on the IPA website at: https://www.gov.uk/government/publications?departments%5B%5D=infrastructure-and-projects-authority

Further information about the Cabinet Office Infrastructure and Projects Authority, and guidance for central government bodies on the requirements for integrated assurance and approvals is available online: https://www.gov.uk/government/organisations/infrastructure-and-projects-authority

Infrastructure & Projects Authority

Cabinet Office

1 Horse Guards Road

London

SW1A 2HQ

# Appendix J:  Evaluation of Possible Site Options

A workshop was held on 27th November 2019 to discuss where, in view of the combined project, possible building work could take place and the merits of each option.    Attendees included senior managers from ULHT, CCG, Pathlinks (pathology provider):

| Position | Organisation |
| --- | --- |
| Deputy Director of Operations, Project Lead | ULHT |
| Matron, Urgent Care | LCHS |
| Patient Representative |  |
| Project Manager, Facilities | ULHT |
| Urgent Care Project Manager | CCG |
| Volunteer, Research & Development, Patient Representative | ULHT |
| Deputy Sister, ED | ULHT |
| Consultant, Emergency Department | ULHT |
| Pathology Site Manager | Pathlinks |
| Associate Director of Estates and Capital Planning | ULHT |
| Senior Commissioning and Performance Manager | CCG |
| Capital Projects Manager, Facilities | ULHT |
| Consultant Architect, Facilities | ULHT |

A range of options had been developed by ULHT consultant architect in response to the emerging accommodation schedule with do minimum, intermediate and do maximum options.  In addition, the ULHT estates strategy had identified adjacent buildings in poor condition, which, with some moves of existing occupants, could be a good option to raise and rebuild.

After some debate the preferred options for a possible site location were options 4, 5, 11 and 12 with option 4 as the preferred, 5 and 12 as the preferred do minimum and 11 as the preferred do maximum.  A table summarising the debate around the options is given below.  Reasons why some designs were discounted are given in the disadvantages table for each option:

| Option | Scope | Outcome |
| --- | --- | --- |
| 1 | Do maximum option | Discounted |
| 2 | Intermediate option | Discounted |
| 3 | Intermediate option | Discounted |
| 4 | Do minimum option | Preferred way forwards |
| 5 | Intermediate + option | Carried forwards as a do minimum option |
| 6 | Intermediate + option | Discounted |
| 7 | Intermediate + option | Discounted |
| 8 | Intermediate + option | Carried forwards as a do more option |
| 9 | Intermediate + option | Discounted |
| 10 | Do maximum option | Discounted |
| 11 | Do maximum option | Carried forwards as a do maximum option |
| 12 | Do minimum option | Carried forwards as a do minimum option |

Option 1 – do minimum

This was a reduced look at the two separate options presented within the original strategic outline cases – a separate build for both the UTC and for an expanded resus.  A small, single storey extension on one side of the ED to increase the existing 4 bay resus area to 6 bays and the construction of a new two-storey UTC in front of the ED.  There would be modest road diversions on both sides of the ED.

| Strengths | No need to decant staff from existing accommodation and could phase work around the existing services; Lowest cost option |
| --- | --- |
| Weaknesses | Does not support reconfiguration of the existing ED or improve diagnostic / pathology services. |
| Opportunities | Does provide a UTC and improved resus and as a result would improve patient outcomes to an extent |
| Threats | Requires road diversions, albeit limited, on both the east and south sides of the building. “Land locks” the ED between existing services and the road extensions – no scope for further extension without further road moves |

Option 2 – do maximum

This option effectively described the two original strategic outline cases.  A new build resus extension with full road moves to the south and a new build two-storey UTC extension out from the existing ED.

| Strengths | No need to decant staff from existing accommodation and could phase work around the existing services |
| --- | --- |
| Weaknesses | Does not support reconfiguration of the existing ED or improve diagnostic / pathology services High cost option Poor connectivity between ED and UTC |
| Opportunities | Does provide a UTC and improved resus and as a result would improve patient outcomes to an extent |
| Threats | Extensive road diversions on both the east and south sides of the building. “Land locks” the ED between existing services and the road extensions – no scope for further extension without further road moves |

Option 3 – intermediate option

To the north of the existing ED there is a H-shaped building which currently houses services such as medical physics, cardiology and orthodontics.  This building has significant backlog maintenance issues as set out in the ULHT estates strategy.  The cost of these backlog issues would offset the cost to decant and demolish this building making this an option to reduce potential road works to expand the building.  Several options look at this.

This option would involve decanting the H-block and using an additional courtyard space near OPD to create a space to move displaced staff into.  In the space of the demolished building a new two-storey extension for ED and UTC.  The UTC would sit where the existing ED is located as the front door.  There would be a small road diversion to the south of the ED.

| Strengths | No road diversions to the front of ED No disruption to existing services during construction Would contain most of the core and nice to have elements |
| --- | --- |
| Weaknesses | Road diversions remain to the south Although there is expansion of the existing ED it is limited and would not allow expansion without future road diversion Design would be constrained by having to be “shoe-horned” into the space left from the H block |
| Opportunities | Demolition of H block removes backlog maintenance issues (offset cost of build) Good connectivity between ED and UTC – promoting staff integration and new ways of working |
| Threats | Requires decant of existing services in the H block. Whilst possible to do, needs careful planning to minimise disruption to clinical services |

Option 4 – intermediate option

This option also utilises the “H-block” but does not expand outwards from ED to the south.  Again, a two storey extension with ED moving to the new building and UTC taking over the existing ED space.  The first floor would be used for the office space, training and storage as well as some services such as clinical assessment.

| Strengths | No road diversions No disruption to existing services during construction Financially realistic in view of less building work and no road moves |
| --- | --- |
| Weaknesses | Reduced footprint and expansion of the existing ED is limited Does not allow expansion without future road diversion Design would be constrained by having to be “shoe-horned” into the space left from the H block |
| Opportunities | Demolition of H block removes backlog maintenance issues (offset cost of build) Good connectivity between ED and UTC – promoting staff integration and new ways of working |
| Threats | Requires decant of existing services in the H block. Whilst possible to do, needs careful planning to minimise disruption to clinical services |

Option 5 – intermediate + option

Options for increased footprint were also considered (intermediate + options).  This option includes the “H-block” as a new UTC and a larger road diversion to the south of ED which would allow a resus and office / training extension to the south and west of the existing building.

| Strengths | No road diversions to the front of ED No need to demolish the H-Block (although backlog maintenance issues remain) Contains core and desirable options |
| --- | --- |
| Weaknesses | Work to improve majors in ED would have to be phased as no decant options Major road diversion to the south UTC accommodation would be constrained within the old H building |
| Opportunities | Potential to expand out further without road works Good connectivity between ED and UTC – promoting staff integration and new ways of working |
| Threats | Requires decant of existing services in the H block. Whilst possible to do, needs careful planning to minimise disruption to clinical services Loss of car parking revenue |

Option 6 – intermediate + option

In this option staff would be decanted from the H block and the building demolished.  A new two-storey extension to the north of ED would contain the UTC.  Diversions to the south of the ED allow for the extension for resus as per option 5.

| Strengths | No road diversions to the front of ED Contains core and desirable options |
| --- | --- |
| Weaknesses | Work to improve majors in ED would have to be phased as no decant options Major road diversion to the south |
| Opportunities | Potential to expand out further without road works Demolition of H block removes backlog maintenance issues (offset cost of build) Good connectivity between ED and UTC – promoting staff integration and new ways of working |
| Threats | Requires decant of existing services in the H block. Whilst possible to do, needs careful planning to minimise disruption to clinical services Loss of car parking revenue |

Option 7 – intermediate + option

Diversion of the existing roads to the south and east of the existing ED.  Construction of a new two-storey extension for a new UTC at the front of the ED and an extension to the south of the ED to expand majors and resus.

| Strengths | No need to demolish any buildings / decant staff Contains core and desirable options |
| --- | --- |
| Weaknesses | Work to improve majors in ED would have to be phased as no decant options Major road diversions Limited expansion of the existing ED – majors and resus |
| Opportunities | No way into ED without going through UTC Good connectivity between ED and UTC – promoting staff integration and new ways of working |
| Threats | Loss of car parking revenue Compromised ambulance drop off area |

Option 8 – intermediate + option

Decanting the H block and extending and refurbishing this building to create a new UTC.  New extensions east and southwest of the existing ED provide additional space to develop majors and resus.

| Strengths | No need to demolish any buildings No significant road diversions Contains core and desirable options |
| --- | --- |
| Weaknesses | Most of the UTC would have to be designed to fit in the H Block, constraining what could be designed. Work to improve majors in ED would have to be phased as no decant options with limited expansion |
| Opportunities | Good connectivity between ED and UTC – promoting staff integration and new ways of working |
| Threats | Loss of car parking revenue Compromised ambulance drop off area |

Option 9 – intermediate + option

Major road diversions again to the south of the ED with a new two-storey construction for Majors and Resus.  UTC occupies the old ED space and 1st floor above for clinical assessment service, office and training space.

| Strengths | No need to demolish any buildings or decant any staff Purpose build ED with no disruption to existing services Contains core and desirable options |
| --- | --- |
| Weaknesses | Most of the UTC would have to be designed to fit within the old ED, constraining what could be designed. Major road diversion to the south of the ED |
| Opportunities | Potential for further expansion Good connectivity between ED and UTC – promoting staff integration and new ways of working |
| Threats | Loss of car parking revenue ED becomes very remote from the rest of the hospital – theatres, diagnostics etc. |

Option 10 – do maximum option

A full road diversion to the south of the existing ED, with a new, two-storey extension to encompass an entirely new ED with resus and a new UTC.  The existing ED would continue as is until the new build was opened then migrate.  The old ED then freed up for future expansion.

| Strengths | No need to demolish any buildings or decant any staff Purpose build ED and with no disruption to existing services Contains core, desirable and optional elements |
| --- | --- |
| Weaknesses | Major road diversions High cost |
| Opportunities | Existing space freed for other services Custom build building with excellent connectivity between ED and UTC – promoting staff integration and new ways of working |
| Threats | Loss of car parking revenue ED and UTC becomes very remote from the rest of the hospital – theatres, diagnostics etc. |

Option 11 – do maximum option

A full road diversion to the east of ED and Out Patients out to the Skirbeck House building.  Ambulances would be redirected to the South of the building.  A new two-storey extension to the east of the existing ED and H block for purpose built UTC.  New resus and extension to the existing ED.

| Strengths | No need to demolish any buildings or decant any staff Purpose built UTC Contains core, desirable and optional elements |
| --- | --- |
| Weaknesses | Major road diversions across the front of ED High cost Would have to phase the ED extension New ambulance drop of could conflict with other traffic |
| Opportunities | A large area in front of Out Patients is made available for future service expansion / development Good connectivity between ED and UTC – promoting staff integration and new ways of working |
| Threats | Loss of car parking revenue |

Option 12 – do minimum option

A further option was introduced to look at the use of existing buildings more and reducing the specification down to an absolute bare minimum service provision.  The resus area remained the same with a large road diversion to the south of the ED and a small extension to the west.  The UTC was constrained within the existing facility with a smaller extension into part of the H block and infilling a small courtyard area between the two.

| Strengths | Low cost Minimal disruption to existing services during build |
| --- | --- |
| Weaknesses | Major road diversions to the south of ED ED becomes land locked by services to north and west and road to east (potential expansion south through resus UTC is shoe-horned into Existing poor quality building |
| Opportunities | Future work could move the road to the east to expand, but high cost |
| Threats | Loss of car parking revenue Very poor connectivity between UTC and ED, staff would not be able to integrate |

# Appendix K:  Clinical Model Options

# Appendix L:  pathology Solution for Pilgrim Hospital Urgent Care Project

DRAFT

Outline Business Case (OBC)

Title : Pathology Solution for Pilgrim Hospital Urgent Care Project

Division/Directorate : CSS – Path Links

Clinical Lead (if required):

Author : Path Links Pilgrim Pathology Site Manager

| DATE | November 2019 |  |
| --- | --- | --- |
| DOCUMENT VERSION | 1 |  |
| WORKING GROUP MEMBERS | Title: Path Links | Name: |

| Approving Body (where required) | Date Approved |
| --- | --- |
| Trust Board | [insert] |
| Trust Management Board | [insert] |
| Financial Planning Group (advisory forum) | [insert] |
| Divisional/Directorate sign off (ie SMT) | [insert] |
| Speciality Team (if required) | [insert] |

# Table of Contents

Page No

- Purpose of Paper									3

- Background										3

- Current Service Description								4

- Case for Change									4

- Outline of Proposal									5

- Key Assumptions and Dependencies							8

- Financial/Resource Requirements							9

- Summary & Recommendations							11

- Purpose of the Paper

# The purpose of this paper is work up of three possible Diagnostic Pathology Solutions for the Pilgrim Hospital Urgent Care Project.

- Background

    - Provision of diagnostics room within the proposed development of the Pilgrim ED and Urgent Treatment Centre.  Funding announced for 20 health organisations to receive a share of £850M by the Prime Minister on 5th August 2019, work for this project costed at £21.3M.

    - ED staff use multiple requesting pathways, primary WebV system for requesting diagnostic test within Blood Sciences and Microbiology and secondary handwritten requests for Transfusion.  Ttese are reported electronically and available via WebV to the requestor.  POCT completed in ED is recorded in the patients notes, Glucose results upload to UPOC.

    - LCHS currently do not have access to WebV.

    - High rejection rate around samples received from Pilgrim ED currently, data for Sept 2018-2019 showed 14.9% of samples received by the laboratory during the year were reported as unsuitable and required repeating.  Total number 5917/39690 samples reported as unsuitable across blood sciences.

    - Poor compliance for Blood Glucose POCT device EQA returns within Pilgrim ED, resulted in removal of half of the devices during 2019 whilst staff were retrained.  Devices returned once training reached 70%.

    - Staff provision and time constraints on ED staff for POCT, over the last 6 months ED has averaged 2677 blood gases a month.

    - Staff provision and time constraints on ED staff for Phlebotomy, leads to errors reported as unsuitable by Pathology based around sample quality, labelling failures, missed samples, and patient identity in doubt rejections.

    - ULH ED  levels of test requesting high against national figures. Demand Management solution in Version 3 of WebV due 2020.

    - ULH ED levels of cannulation ?  Feedback from ED staff ?

    - Question the value of some POCT currently being completed, design pathways around the POCT adding value and affecting that indivduals pathway.

    - Health Education England (HEE) Conditions - Repetitive Tasks. HEE condition around junior doctors undertaking repetitive tasks with little educational benefit has remained open for several years. This condition relates to junior doctors reporting they have an excessive burden of phlebotomy and POCT duties. Considered to be a “serious issue that has been impacting negatively on the quality of educational and training for several years (2015) and remains largely unresolved”

    - Phlebotomy and POCT included in core skills set for Band 5 nurse and HCSW staff, Recent junior doctor survey (September 2018) indicates nursing staff frequently unable to undertake these duties due to a combinations of staff shortages, lack of training, not considered to be their role or too busy

  - Key Risks

    - HEE requirement looks for Trusts to evidence a reduction in the burden around phlebotomy and cannulation. Failure can result in the condition being passed to the GMC for enhanced monitoring

    - Without intervention, an increase in the volume of patients seen across the new development would lead to a worsening of the current situation negatively impacting on:

- Timeliness of the diagnostic/patient monitoring pathway

- Avoidable delays to diagnostic pathways and patient treatment & discharge

- Poor EQA performance leading to clinical decisions on POCT devices out of consentus

- Increasing demand on front-line clinical staff

- Errors leading to serious incidents and reportable negative events for the Trust

- Current Service Description

POCT within ED covers Blood Gases, Blood Glucose Monitoring and RDT for Pregnancy testing and Urine dipsticks, support by POCT co-ordinator.

Path Links provide on site Pathology laboratory Blood Science service 24/7 and Microbiology 09:00-21:00, out of hours samples are taxi’d to Microbiology at Scunthorpe hospital within the Path Links network.

- Case for Change

# The development of a new ED and UTC Diagnostic facility including POCT on the Pilgrim site with ULHT managing the ED and LCHS managing the UTC.  Aim of the preferred option would be a significant benefit to front line clinical operations and to patient care in that:

- Front line clinical staff time is released for other activities, reducing pressure on junior doctor and ward staff

- Address the current rejection rates and improve real-time patient diagnostic demand leading to timely clinical decisions and patient discharge

- Provides additional capacity to support activity growth

- Provides greater flexibility of service provision and availability

- Outline of the three Proposal’s

Option 1

Diagnostic room with POCT within ED/UTC, run by ED/UTC staff, with 2 x Phlebotomist

Staff from the ED/UTC areas running the POCT,  completing the daily task list for all platforms

- Performing POCT testing on ED/UTC samples for patients, recording these within the patient notes.

- Performing Blood Gases, base for the Blood Glucose and Ketone monitors and RDT POCT for pregnancy and Urine dipstick.

- Clinical staff perform daily IQC and monthly EQA returns on the POCT devices, perform maintainance procedures and deal with any problems, communicate with the Path Links laboratory staff, POCT Co-ordinator, Diabetes team and providers.

- Standard Operating Procedures (SOP) for the Clinical staff to follow providing a consistant approach to ED/UTC POCT.

- Provision of two Phlebotomy staff to support both ED and UTC areas, need to review the work up around foot fall into both departments.

- Phlebotomy training within both areas, based around the needle and holder method, butterflies and cannula draws taken from Major/Rheus patients only,

- Bottle collection system provider can provide additional training as part of current Pathology Collection System tender.

Option 2

Diagnostic room with POCT within ED/UTC, run by additional Path Links staff, with 2 x Phlebotomist

Looking at providing staffing from the laboratory Band 3 staff group, additional requirement for recruitment of six Biomedical Assistants (BMA).  Working on 24/7 operation within the diagnostic room would require a minimum of 5.51 WTE based on sickness and annual leave at 23%. Prosposal that the BMA rotate through both the blood sciences laboratory and the proposed POCT unit.

Note this would require a consultation with this staff group to change there working practise to include the POCT facility within the ED/UTC.

The BMA staff can run the POCT facility:

- Performing POCT testing on ED/UTC samples for ED/UTC clinical staff.

- Perform Blood Gases, base for the Blood Glucose and Ketone monitors used in tandem by Clinical staff and BMA.  RDT POCT for pregnancy and Urine dipstick.

- Requests can be booked in by BMA staff on to the Laboratory LIMS systems so results are available via WebV for clinical staff to view eg electronic results, improved Governance across ED/UTC Pathology diagnostics. Benefits clinical teams across the trust using WebV. Note on WebV version 3 Blood Glucose results will be available.

- BMA staff can perform daily IQC and monthly EQA returns on the POCT devices, perform maintainance procedures and deal with any problems, communicate with the POCT Co-ordinator, Diabetes team and providers.

- BMA staff trained to perform phlebotomy, providing support for clinical staff within ED/UTC

- Provision of two Phlebotomy staff to support both ED and UTC areas, need to review the work up around foot fall into both departments.

- Phlebotomy training within both areas, based around the needle and holder method, butterflies and cannula draws taken from Major/Rheus patients only,

- Bottle collection system provider can provide additional training as part of current Pathology Collection System tender.

- Standard Operating Procedures (SOP) for the BMA to follow to provide a consistant approach to ED/UTC POCT.

Option 3

Ultilise the onsite Path Links Laboratory, addition of  2 x Phlebotomist and 1 Porter with the ED/UTC.

This option,  working around our KPI of 60 minutes for ED samples,

- Clincical staff maintain current processes for POCT.

- Phlebotomy training within both areas, based around the needle and holder method, butterflies and cannula draws taken from Major/Rheus patients only,

- Bottle collection system provider can provide additional training as part of current Pathology Collection System tender.

- Addition of a dual air tube system with units positioned within both the new ED and UTC.

- Portering provision for the ED/UTC area, provide backup when lost of air tube system to transport samples to the onsite labvoratory.

- Key is the 15 minute window from vein to laboratory reception,  would require regular auditing to highlight any delay’s.

- Provision of two Phlebotomy staff to support both ED and UTC areas, need to review the work up around foot fall into both departments.

- Continue performing Blood Gases, Blood Glucose and Ketones and RDT POCT for pregnancy and Urine dipstick POCT within ED.

Solution based on improving the quality and turn around of samples into the site based pathology laboratory, looking at Phlebotomy and Sample transport (air tube/porters) across ED/UTC.

Potential POCT Solutions

- Troponin POCT

Contacted ULHT Cardiology, Dr XXXXXXXXXXXX Consultant Cardiologist and XXXXXXXX Consultant Nurse Cardiology/ Associate Chief Nurse (NMP), Cardiology

The sensivity and the specificity is not high enough to use within the ED/UTC environment and would not meet the Trust Cardiology guidelines for assessment of acute chest pain of possible origin.

Note the sensitivity is the ability of a test to correctly identify those with the disease (true positive rate), whereas test specificity is the ability of the test to correctly identify those without the disease (true negative rate).

ULHT Cardiology are working on new chest pain guidelines for the Trust that will include moving to single early troponins completed at 2 hours post pain presentation. This will reduce the time to result by 2/3rds due to a single test instead of multiples.

- BNP POCT

Contacted ULHT Cardiology, Dr XXXXXXXXXXXX Consultant Cardiologist and XXXXXXXX Consultant Nurse Cardiology/ Associate Chief Nurse (NMP), Cardiology

Their view is yes international guidelines state a need to assess natriuretic peptide in suspected heart failure however this is not time critical and (unlike troponin) will rarely if ever facilitate discharge from A&E in there opinion.

Currently the test is available via the laboratory and history would support that it could be overused with POCT at considerable cost to the trust. If you start doing it on all undifferentiated SOB then you will get a load of people labelled as Heart Failure who are not. Cardiology don’t see a role in an UTC/ambulatory setting.  Look at setting a KPI standard for BNP processed by the laboratory.

- D-Dimer POCT

Request for age related D-Dimer giving a quantitive figure, a normal D-Dimer result can be used as a negative indicator to rule out acute deep vein thrombosis and pulmonary embolisms.  Multiple options available for POCT D-Dimer, requires submission POCT Implementation documents to the ULHT POCT team.

Currently the test is available via the laboratory and history would support that it could be overused with POCT at considerable cost to the trust.  The laboratory currently report a qualitive result for D-Dimers (Positive or Negative).  A number of UK trusts are introducing age related D-Dimer quantitive reporting and this could be created for ED/UTC for requesting on these patients.

Our provider has put me in touch with The Princess Alexandra Hospital NHS Trust in Harlow Essex who have completed some work on age related D-Dimer quantitive reporting, I will feed this back to the working group at a later meeting.  This has also been raised to the Path Links Haematology Techical working group for further discussion.

Any POCT would require a full Procurement tender , further suggestions for POCT solutions can be worked into solutions 1 & 2.

- Key Assumptions and Dependencies

- Modeling foot fall for the new ED/UTC development

- Ability to recruit staff.

- Ability to train staff to a level of competence using these devices and systems.

- Ability of staff to maintain competence.

- Ability to meet Quality control standards around IQC And EQA returns for all registered devices.

- Capacity of Trust IT and WebV team to support implementation of additional POCT, that can be interfaced into the Pathology LIMS system.

| Area | Yes/No | Further Detail if Yes | Agreed with |
| --- | --- | --- | --- |
| Estates & Facilities (domestics, portering, catering etc. | Yes | Air tube system x 2 ED/UTC, Portering support, Diagnostic room with new development | TBC |
| Diagnostics | Yes | POCT team support, Providers training/support | TBC |
| Pharmacy | No |  |  |
| Path Links | Yes | Recruitment & training | TBC |
| IT / IM&T | Yes | Interfacing additional POCT systems, WebV, ULHT IT | TBC |
| Other Divisions/Directorates | No |  |  |
| Procurement | Yes | Tender for selected POCT | TBC |
| Contracting | Yes | Potential contracts providers/Path Links NLAG, | TBC |
| Governance | Yes | Trust, Path Links | TBC |
| CQC registration | No |  |  |
| Legal implications | No |  |  |
| Equality & diversity | No |  |  |
| Communications Team | No |  |  |
| Transport | No |  |  |
| Standards (fire, infection control etc.) | No |  |  |

- Financial outline (financial template to be added as an appendix in later version)

Based on mid-points AfC Band 2 2023-24 £24,032.00,  AfC Band 3 2023-24 £25,700.00.

Salary figures with On costs calculated on current levels with a percentage of 2.9% uplift year on year

*AfC unsocial hours premium rates applied where applicable.

| Option 1 : Diagnostic room within ED/UTC, run by ED/UTC staff, with 2 x Phlebotomist hours TBC |  |  |  |
| --- | --- | --- | --- |
| Assumed start date 1st April 2023 |  |  |  |
| No change in income or other costs |  |  |  |
| Hours of clinical staff to be released TBC |  |  |  |
|  | 2023/24 (£) | 2024/25 (£) | 2021/22 (£) |
| Income | 0 | 0 | 0 |
| Revenue Cost: 2 x WTE Band 2 | £48,064 | £48,064 | £48,064 |
| Revenue Benefit: (Time released other staff) | TBC | TBC | TBC |
| Net Revenue Cost: | TBC | TBC | TBC |
| Non-recurrent costs (one off costs) | 0 | 0 | 0 |
| Capital | 0 | 0 | 0 |
| Total Expenditure (funding request) | TBC | TBC | TBC |
| Net Margin | NA | NA | NA |
| Option 2 : Diagnostic room with POCT within ED/UTC, run by additional 6 Path Links staff 24/7, with 2 x Phlebotomist hours TBC |
| Assumed start date 1st April 2023 |
| No change in income or other costs |
| Hours of clinical staff to be released TBC |

|  | 2023/24 (£) | 2024/25 (£) | 2021/22 (£) |
| --- | --- | --- | --- |
| Income | 0 | 0 | 0 |
| Revenue Cost: - x WTE Band 2 6 x WTE Band 3 plus *AfC unsocial hours premium rates applied where applicable approximately 25% £6,868.16 with year on year uplift. | £48,064 £154,200* £195,409 | £48,064 £154,200* £195,409 | £48,064 £154,200* £195,409 |
| Revenue Benefit: (Time released other staff) | TBC | TBC | TBC |
| Net Revenue Cost: | TBC | TBC | TBC |
| Non-recurrent costs (one off costs) | 0 | 0 | 0 |
| Capital | 0 | 0 | 0 |
| Total Expenditure (funding request) | TBC | TBC | TBC |
| Net Margin | NA | NA | NA |

Option 3 : Ultilise the onsite Path Links Laboratory, addition of 2 x Phlebotomist and 1 Porter with the ED/UTC hours TBC.

Assumed start date 1st April 2023

No change in income or other costs

Hours of clinical staff to be released TBC

|  | 2023/24 (£) | 2024/25 (£) | 2021/22 (£) |
| --- | --- | --- | --- |
| Income | 0 | 0 | 0 |
| Revenue Cost: 3 x WTE Band 2 | £72,096 | £72,096 | £72,096 |
| Revenue Benefit: (Time released other staff) | TBC | TBC | TBC |
| Net Revenue Cost: | TBC | TBC | TBC |
| Non-recurrent costs (one off costs) | 0 | 0 | 0 |
| Capital | 0 | 0 | 0 |
| Total Expenditure (funding request) | TBC | TBC | TBC |
| Net Margin | NA | NA | NA |

- Staff requirements, need to be adjusted around the predicted work flow from foot fall into the new development.  Numbers and working hours will need to be modelled on work volumes to provide maximum efficiency.

Non-pay costings will require predicted activity data for the POCT Solutions to compare the costs associated with the onsite laboratory against a POCT device.

All costings for Non-pay are 2019-20 , currrent laboratory costing for ULHT

| Test | Cost |
| --- | --- |
| BNP | £24.93 |
| D-Dimer | £8.60 |
| Glucose POCT | 18.5p |
| Ketones POCT | £1.69 |

Glucose are charged to ULHT cost per strip based on 100 test strips costing £18.54 per pack, so 18.5p a test this includes the Connectivity/Training/Support/EQA costs.

Ketones are charged to ULHT cost per strip based on 50 test strips costing £84.66 per pack, so £1.69 a test this includes the Connectivity/Training/Support/EQA costs.

Blood Gases are charged to ULHT per test, but this is calculated on test performed against reagents used and covered in the Path Links Contract.  ULHT are billed for EQA separately.

RDT are ordered via RDC by the wards.

Using Roche as a example supplier solution, as they are the currently Gas Analyser supplier for ULHT and have units in LCHS minor injuries units at Skegness and Louth. These are costing for purchasing test kits with no operating costs included.

| Product | Product Code | Unit Price 2019-2020 |
| --- | --- | --- |
| Roche H232 Unit with Scanner with battery and base unit | 06740758001 | £1,583.56 |
| Roche CARDIAC D-Dimer (10 tests) | 04877802190 | £80.40 |
| Roche CARDIAC Control D-Dimer | 04890523190 | £46.64 |
| Roche CARDIAC proBNP+(10 tests) | 05533643190 | £339.49 |
| Roche CARDIAC Control proBNP | 04890493190 | £84.87 |

Number of Requests from ED at Pilgrim over the last 12 months 2018-2019.

BNP – ED at Pilgrim requested 329 primary orders not including add-ons.

D-Dimer – ED at Pilgrim requested 3584

- Summary and Recommendation

The preferred Pathology solution for the proposed Pilgrim Hospital Urgent Care Project would be option 2: a Diagnostic POCT facility staffed by Path Links laboratory staff within the new development or 3: using the current UKAS accredited onsite Blood Sciences laboratory.

Cost is a key factor as POCT is not a cheap solution, savings associated are calculated by reduced admissions and shorter stays due to patient being put on pathways quicker.  To provide costs for the POCT solution it requires predicted activity for these pathways within the new development.

Pathways play a key part in the use of POCT solutions, patients who fit that pathway need to be identified by the clinical teams and once POCT results are available they require action to affect the pathway in  a positive way e.g. admit or discharge the patient which in turn leads to short hospital stays and a positive patient experience.

Specifically D-Dimer with the volumes of requests ED are currently making, a POCT solution would need introducing with strict guidance based around the pathway to prevent it being abused and over used at asignificant cost to trust.

All solutions include a phlebotomy provision to support the clinical teams and help improve the sample quality.  Better management of pre-analytics (sample quality), addressing the current rejection rates and improve real-time patient diagnostic demand leading to timely clinical decisions and patient discharge.

Porter cover and Air tube stations within both areas is key to support the 15 minute ‘vein to lab’, to facilitate the 60 minute KPI for ED.

Path Links staff working within the facility would lead to improvements in governance, results would be booked into the local LIMS and results  would be accessable electronically via the WebV system, available to clinical teams throughout the Ed/UTC and hospital.

Free clinical staff to focus on patient care and treatment, positive effect on staff and patients, improving patient flow at the front door of Pilgrim ED/UTC.

# Appendix M:  Medicine Division Staffing Plan

Introduction

On 5th August 2019, Prime Minister Boris Johnson visited The Pilgrim Hospital site to announce funding for 20 organisations to receive a share of 850M to improve services.  This included the allocation of £21.3M to Pilgrim Hospital.

This plan sets out the vision for workforce development, triangulating demand and capacity and workforce needs to ensure that the new build will not only be fit for the future from an estates perspective, but that the workforce needs have been fully considered.  Our patients remain at the heart of everything we do, and this plan has a clear focus on fostering a culture of inclusion and belonging, as well as action to grow our workforce, train our people, and work together differently to deliver excellent patient care.

The plan focusses on three key areas:

Growing a multidisciplinary workforce, including creating a resilient senior decision-maker layer of Emergency Medicine staff

Reducing attrition in the ED

Improving retention of staff working in ED

It covers all clinical staff working in EDs who interact with patients including doctors, advanced care practitioners, nursing staff and physician associates as well as other multi disciplinary clinical staff.

The workforce challenge in Emergency Medicine

Staff working in Emergency Departments aim to deliver high quality patient care for all patients whether they present with minor or critical life-changing conditions.  Over the past few years, the numbers of staff working in our EDs have increased in both the medical and nursing workforce, however as have attendances, admissions and the overall complexity of the needs of patients.

Whilst Pilgrim ED has historically struggled to recruit substantive staff; both medical and nursing; significant investment combined with targeted recruitment programmes have allowed the department to recruit, retain and develop a substantive workforce.

This work is underpinned by a commitment from the Organisation to ensure that our workforce is fit for purpose.  Annual establishment reviews for the nursing team are undertaken, led by the Director of Nursing; based on real time demand and capacity work with recommendations fed directly into Trust Board.

United Lincolnshire Hospitals NHS Trust has recently commissioned a full Medical Workforce Management Project to ensure our medical workforce is able to deliver the care we need both now and in the future.

Both of these programmes of work link with the Pilgrim ED Workforce plan to support the workforce needs for the new department.

Whilst this plan is aspirational, there is acknowledgement that workforce challenges within the NHS have been recognised at a national level.  The new build at Pilgrim Hospital will provide an environment fit for purpose to deliver emergency care not just for the immediate future but for the next fifty years.  Patient and departmental safety is central to all decision making, and ensuring that the department is able to safely staff all areas is paramount to both.  A realistic recruitment trajectory will be developed ensuring full oversight of the workforce position.  Workforce will be identified as a risk to the project and mitigations will include staggered opening of the areas within the new build ensuring each area is appropriately staffed prior to use.

Demand and Capacity - Estates

The Urgent Treatment Centre (UTC) and ED estate capacity requirements have been assessed using the following sources:

LCHS data from December 2019 (when the UTC was first introduced) to August 2021

ULHT ED date from January 2019 to September 2021

The Office for National Statistics (ONS) growth forecast for the area of 6%

Table 1 - Current vs required estates needs for the department.

|  | Current Cubicles | Required Spaces / Cubicles |
| --- | --- | --- |
| Resus | 4 | 8 |
| Majors | 8 | 43 (11 majors + 6 RAIT + 3 speciality + 3 step up + 20 F2S |
| UTC (inc minors) | 6 | 9 (8 consultation + 1 observation / phlebotomy room) |
| Paediatrics | 1 | 4 |

Demand and Capacity - Workforce

4.1    Medical Workforce

The ED workforce Demand and Capacity modelling undertaken utilised the following assumptions:

Identification of the optimal site-specific workforce required for Tier 1 (Junior Doctors) Tier 2 (Middle Grade Doctors) and Tier 3 (Consultants_

Minimising the average cost / risk (overstaffed vs understaffed) by factoring staffing capacity and desired demand

Modelled at 80 percentile demand requirement

Health Care Professional productivity

Utilised data period from March 2019 – February 2020

Table 2 – Pilgrim ED Medical Workforce Requirements

In addition to the demand, it is important to ensure that there is sufficient cover to ensure all areas in the new department are staffed including:

Paediatric

Resus

Rapid Assessment and Treatment (RAT)

Majors

Fit 2 Sit

Walk in RAT

Nursing Workforce

ULHT utilised the Baseline Emergency Staffing Tool (BEST) to support the annual establishment review led by the Director of Nursing.  The tool has been developed by the RCN Emergency Care Association (ECA) and Faculty of Emergency Nursing (FEN).  The tool allows:

Analysing the volume and pattern of nursing workload in the ED

Track this against the rostered staffing levels

Calculate the whole time equivalent workforce and skill mix which would be required to provide the nursing care needed in the department during the audit period

The tool does not produce recommended staffing levels but will allow EDs to work locally to reduce any disparity between workload and staffing for example improving patients pathways, departmental processes rota demands and actual staffing.

The BEST calculations work by using nurse-to-patient ratios in the various dependency categories.  The ratios used are:

Total dependency – 2 nurses to 1 patient

High dependency – 1 nurse to 1 patient

Moderate dependency – 1 nurse to 2 patients

Low dependency – 1 nurse to 3.5 patients

The hourly data sets used by BEST are:

Patient dependency volume in the department using the Jones Dependency Tool

The total number of staff rostered to be clinical on shift in the department

A calculation will also provide an indication of what skill mix breakdown is required in the whole time equivalent workforce in the ED.

Following the annual data collection utilising the BEST calculations, the nursing team within the Clinical Business Unit analyse output and propose an establishment for Director of Nursing approval pending agreement by the Trust Board.

Medical Workforce

Triangulating the departmental demand and capacity, workforce demand and capacity and the future estates requirements the future workforce requirements have been calculated.  The uplift in WTE ensures the following:

Dedicated Paediatric Middle Grade

Additional Resus Middle Grade

Dedicated Fit 2 Sit Middle Grade

Table 3 – Proposed Medical Establishment

|  | Current | Proposed |
| --- | --- | --- |
| Jr | 12 WTE | 24 WTE |
| Middle Grades | 25 WTE | 38 WTE |
| Consultant | 12 WTE | 15 WTE |

Nursing Workforce

The nursing establishment requirements will continue to be reviewed on an annual basis; however the anticipated template below takes into account the increase in estate, and increase in demand identified in the demand and capacity.

Table 4 – Proposed Nursing Establishment

| Current Estate | Current Template | Future Estate | Proposed Template |
| --- | --- | --- | --- |
| Nurse in Charge | 1 | Nurse in Charge | 1 |
| Pre Hospital Practitioner | 1 | Pre Hospital Practitioner | 1 |
| Fit 2 Sit (16 spaces) | 2 x RN 1 x HCSW | Fit 2 Sit (23 spaces) | 3 x RN 1 x HCSW |
| Majors & RAT (15 spaces) | 5 x RN 3 x HCSW | Majors & RAT (23 spaces) | 6 x RN 3 x HCSW |
| Paeds (1 cubicle) | 1 x RN 1 x HCSW | Paeds (4 cubicles) | 2 x RN 1 x HCSW |
| Resus (6 spaces) | 3 x RN 1 x HCSW | Resus (8 Spaces) | 4 x RN 2 x HCSW |
| Triage 2 streams | 2 x RN 1 x HCSW | Triage 3 streams | 3 x RN 2 x HCSW |
| TOTAL | 15 x RN 7 x HCSW |  | 20 x RN 9 x HCSW |

Advanced Clinical Practitioners

Advanced Clinical Practitioners (ACP) already work within the ED.  As experienced registered healthcare practitioners, their practice is characterised by a high level of autonomy and complex decision-making, underpinned by a Masters degree that encompasses clinical practice, management and leadership, education and research.

The current establishment for ACPs at Pilgrim is 10 WTE.  This establishment covers both ED and SDEC.  To provide sustained 2 x ACPs in ED and 2 x ACP in SDEC at Pilgrim this establishment will need to increase to 14 WTE.  This uplift accounts for an 80/20 split between clinical and non clinical activity as per RCEM guidance.

Table 5 – Proposed ACP Establishment

| 08:00 – 20:30 | 1 | 1 |
| --- | --- | --- |
| 09:30 – 22:00 | Intermittent cover due to workforce | 1 |

Supporting wider professional groups in the ED

The vision to develop a stable, well supported and resilient workforce in EDs will enable improved and sustainable patient care, will alleviate pressure on the existing workforce, and will improve finances through reducing staff turnover and use of locum and agency staff on the short, medium and long-term.

The operationalisation of this plan will include the development on a multi professional workforce.  The benefits of including multi professional working has been well documented and recognised as adding breadth and depth of cover in the EDs.

Consideration of wider professional groups will include but are not limited to:

8.1   Physician Associates

The Physician Associate (PA) is a healthcare processional who, while not a doctor, works to the medical model, with the attitudes, skills and knowledge base to delivery holistic care.  Currently a high number of PA and PA students have a bioscience qualification, and their broad skills mix means they can practice across a range of medical specialties.

Pharmacist Clinicians

Pharmacist clinicians have advanced clinical health assessment skills and can support the ED with:

Undertaking medicines-focussed duties such as pre-discharge medicines optimisation, medicines reconciliation and prescribing

Optimising the use of medicines on admission to emergency and acute care

Supporting medicine reconciliation pre-discharge of acutely ill patients

These duties are often undertaken by junior medical staff who face significant demands on their time.  Clinically trained pharmacist prescribers can work alongside junior doctors to take on some of these duties to free up doctors time to focus on more complex clinical work.

Recruitment Strategy

The recruitment of qualified and skilled staff to ensure the delivery of the best possible care continues to be a priority not just for the ED but the Trust as a whole.  Whilst recruitment remains challenging, progress has been made within Urgent and Emergency Care.

In February 2020 the Trust agreed to support a significant uplift in medical staff for the EDs at both Lincoln County Hospital and The Pilgrim Hospital.  Since the increase in the Establishment, a targeted recruitment campaign has been undertaken and currently the department has no medical vacancies against establishment.

The Urgent and Emergency Care Clinical Business Unit (CBU) is committed to building on successful recruitment initiatives to support the establishment by:

Developing CBU recruitment plans as part of the wider workforce planning process

Support the recruitment and retention of new roles such as Physicians Associates / Pharmacist Clinicians

Continue to focus and develop great employee experiences throughout the recruitment, on-boarding and induction process

Provide staff with the right opportunities to develop and build careers within their specialty of choice ensuring staff feel valued in their role

Continue to support our in house CESR training and rotation programme

The strategic framework for 2020-2025 provides the future direction for the organistaion, firmly recognising our people as one of the four strategic objectives.  Providing a modern, progressive workforce will deliver well led services and support our staff to feel valued, motivated and proud to work in ULHT.

# Appendix N:  SOP for Management of Patients in ED

This document contains several embedded documents that have been removed, available on request.

Standard Operating Procedure for the Management of Patients within the Emergency Department

Introduction

This standard operating procedure (SOP) has been developed to ensure safe, equitable and timely access for patients presenting at Pilgrim Hospital Emergency Department (ED) and beyond. This SOP outlines the process used by ULHT and partner organisation staff to complete the initial assessments of ED patients and how they should progress through the department. It has been developed to reflect the improved processes and protocols following Royal College of Emergency Care guidance with input from Emergency care specialists at NHSi. (Ref: http://www.rcem.ac.uk/RCEM/Quality_Policy/Clinical_Standards_Guidance/RCEM_Guidance/RCEM/Quality-Policy/Clinical_Standards_Guidance/RCEM_Guidance.aspx )

This standard operating procedure is based on the National Standards for non-elective admissions, which are in line with the Royal College of Emergency Medicine (RCEM) recommendations, Guidelines and Urgent Care standards.  It formalises the process of directing the patients to appropriate pathways as soon as they arrive, either by themselves or by ambulance, so that they can be assessed and managed by the appropriate people, with the appropriate skills.

Initial Assessment

In-line with RCEM Guidance the three main objectives of clinical assessment are:

- Improving Safety.

- Identifying acuity to ensure that the most time-critical patients are treated by the right service within appropriate times frames and that appropriate prioritisation occurs for the remainder.

- Improving efficiency in the system to ensure patients do not wait unnecessarily.

Key Principles

- The front door of the ED should be managed by the ED and fall within its quality improvement and governance systems.

- Any process of navigation or streaming, should be designed so that patient safety is paramount.

- Any intitial assessment process should improve the quality of care provided for patients.

- If patients are advised to attend the ED by other NHS services, navigation and streaming decisions should acknowledge this.

Navigation and Streaming Pathways for Initial Assessment. Walk-Ins and Self Presentations.

Patients that self present at ED main reception undergo a concurrent navigation process undertaken by streaming staff whilst booking in. Please see below flow chart regarding this stream of patient. Principles include:

- Registration, Streaming & Triage should be performed as soon as possible but within 15 minutes of arrival.

- Mancester Triage Score should be obtained for all A&E patients presenting via triage, including paediatrics, within 15 mins

- All paediatric patients should have a set of observations recorded.

- Clinical streaming practitioners should work to the agreed Service Specifications. Embedded below:

- If delays begin to build up in the registration, streaming & Triage process (over 15 minutes) these should be escalated to the Nurse in Charge (NIC) and Emergency Physician in Charge (EPIC)of the department. Actions to take include additional admin support at reception and the consideration of an additional streaming practitioner (Escalation action card attached below).

GP Urgent Care Patients

Patients who are streamed to the Urgent Care GP service can expect:

- To be assessed and treated according to agreed service specification:

- To not wait longer than 1 hours to be seen.

- If the wait is longer than 1 hour to be assessed by a clinician in triage.

- If required, to be referred back into the ED Department via a referral to the NIC/EPIC.

- Joint Clinical Governance Processes between providers to review service specifications and quality/performance indicators outlined within service specifications.

See and Treat/Minor Injuries/Illness Patients.

Minor injuries/illness patients can be directly seen without additional triage or assessment post streaming. Advantages include that patients are seen directly by a single appropriately trained practitioner who can complete the episode of care for that patient. As a safeguard for this group of patients if they are not seen within 1 hour the patient will have a clinical assessment by a clinician in triage.

Patients for Majors/Triage

Walk-in patients, or those referred from inside the Hospital that are deemed to be ‘Majors’, need to be dealt with via the standard triage process, and this will be immediately documented in the patients’ ED card following registration.

The documentation must consist of…

- Triage Nurse’s name

- Date

- Time

- Presenting complaint/s

- Discriminator from MTS algorithm

- Pain score and offer analgesia via PGD

- Triage category as per National Triage Scale

- Triage category must also be completed on the Medway system

- Who has accompanied the patient

- Safeguarding alerts/other triggers on Medway

While triaging children, in addition to above, consideration must also be given to safeguarding concerns, including…

- History

- Previous attendances

- Where necessary, request a safeguarding plan check with the child safeguarding department

Document any concerns and follow safeguarding referral process

Navigation and Streaming Pathways for Initial Assessment. 999 Ambulance Presentations.

Patients that enter ED via the ambulance service should either go straight into The Resus Area or to the Rapid Assessment and Initial Treatment (RAIT) area and handover to an appropraitely qualified RAIT Team member/ Resus Doctor. This process should be completed within 15 minutes. The RAIT or Resus practitioner should complete a Mancester Triage Score and enter this upon Medway within 15 minutes.

If ambulance crews are waiting longer than 15 minutes to handover then patients should be managed using the agreed EMAS ( East Midlands Ambulance Service) and ULHT ( United Lincolnshire Hospitals Trust) polices and procedures which are embedded below:

Pre Handover Practitioner SOP

EMAS Clinical Handover Procedure

EMAS Co-horting Guidance

EMAS Flow Chart

EMAS Pre-Handover Document

All patients that have been waiting for 15 minutes or more with the ambulance crew will be assessed by a suitably qualified practitioner using the Pre-Handover Document. As a minimum the following will be established and documented:

- Time of arrival

- Name/Age

- Presenting Complaint

- Manchester Triage Score

- NEWS/PEWS

- Monitoring of Clinical Handover Procedure.

ULHT staff will continually and consistently maintain oversight of each patient in the handover queue via the EMAS crews and on an hourly basis (as a minimum) and document on the embedded EMAS Pre Handover Record Form.

The Pre-Hospital Practitioner will discuss with the Nurse in Charge of ED the condition and NEWS/PEWS score of all the patients in the queue. Patients should be handed over in time order unless the clinical condition of the patient indicates otherwise. Under these circumstances this will be agreed between the NIC, EPIC, PRP and Ambulance Crew.

The ED NIC must prioritise the sickest patient for handover and if still unable to off load the patient the NIC must inform the EPIC and escalate to the Site Duty Manager.

Ambulance delays (15 minutes or more) must be escalated to the Site Duty Manager (SDM) and Matron for department.

The SDM/Matron should review the department and in conjunction with the NIC and EPIC decide upon what action is required to enable ambulance crews to handover patients. This could include opening additional RAIT cubicles, allocating additional staff to the department or creating timely flow out of the department. This is not an exhaustive list of actions to take and these will require review depending on department circumstances.

If appropriate escalation actions are not followed this must be reported and recorded via the incident management system.

RAIT Handover Process

RAIT describes the process that a senior clinician is based as far forward in the ED process as possible and sees the patient as soon as possible after their arrival. That clinician can make decisions about that patients care and disposition early in the patient’s stay.

Guiding principles for the RAIT process include:

- Any suitably qualified practitioner that is working in RAIT ( Nurse, AHP, Doctor) can take the clinical handover from the ambulance crew.

- Handover to RAIT practitioners does not have to be given by the initial ambulance crew on scene. This can be given by a co-hort ambulance crew.

- Clinical handover should not take longer than 5 minutes.

- The RAIT process should be completed in 20-30 minutes depending on the patient.

- Up to 4 RAIT cubicles can be opened with RAIT staff. Consideration should be given if required for additional staffing in RAIT depending on acuity and volume of patients.

- Once RAIT process complete patient should move into cubicles or fit to sit if appropriate.

If all RAIT cubicles are in use and patients cannot move out of them due to lack of appropriate clinical space within the department this should be escalated to the NIC and EPIC immediately.

The NIC and EPIC should then review department and establish what actions are required to free up RAIT cubicles and undertake those actions.

Early escalation to the Matron and SDM should occur to assist in creating department space to allow RAIT to work effectively.

Room Escalation and Corridor Nursing

At times of extreme pressure there may be times, or a necessity for, patients to be  treated in the ED corridor or in areas of escalation.  The SOP below is designed to provide guidance to how these patients will be cared for from a Nursing perspective, the additional workforce requirements and how those Nurses will be allocated throughout the department.

Secondary assessment

Following on from a patients arrival and initial assessment, Patients are formally seen and clerked in chronological order by the junior and/or Middle grade doctors on the shop-floor depending on clinical need.

- The doctor / ACP doing the second assessment picks up the ED card from the ‘Majors’ box based on clinical need, then in Chronological order.

- They book the patient under their name on Medway as ‘Responsible Clinician’.

- After taking the detailed but relevant history and performing appropriate physical examination, further plan of action is decided after discussion with the Middle-Grade or Consultant on the shop-floor.

- If any more investigation is deemed necessary, the junior doctors should first discuss the patient with the senior doctor on the shop-floor in order to avoid unnecessary investigation.

- All the FY-2 and GP Trainee doctors must discuss their patients with the seniors before referring to a specialty or discharging their patients. The name of the senior doctor must be clearly documented in the ED notes.

- Every patient seen by an FY-1 doctor must be physically seen (not just discussed with) by a senior doctor. The senior doctor should sign and date in the ‘Senior Review’ box of the ED card.

- Any further treatment (medications etc.) must be prescribed in the ED card, timed, dated and signed according to the Trust’s prescription policy.

- Medications such as morphine should be clearly prescribed as ‘Morphine sulphate 1-10 mg titrated i.v.’

- Referral to the specialties should be ideally be made by 2 of patients’ arrival. The ‘Decision to Admit’ (DTA) time should be clearly mentioned in the ED notes as well as on Medway. The NIC should also be informed at the same time, so that they can request a bed for the patient via the Operations teams on appropriate ward.

- All patients (admitted or discharged) must have their discharge summary written and coding completed on Medway at the same time as when the decision is made.

- It is sometimes prudent to print a copy of the GP letter and hand it over to the patients before discharging them, if they are from out of the County or if they are not registered with their GP yet.

- Patients must be reviewed by the other specialties within 30 minutes of the referral.

- Any delay with a speciality response must be escalated to the EPIC who will then contact the Speciality Consultant directly as per Inter-professional Guidelines.

- Patients deemed to have predominantly social problems after reasonable assessment to rule out any acute ‘Medical’ cause for their attendance should be referred to the Community in-Reach (CIR) Team. These patients must have ‘Medically Fit for Discharge’ clearly documented in their ED notes. If these patients need to stay in the hospital overnight to be reviewed by CIR team the next morning, following must be completed…

  - All investigation reports (blood tests, imaging) must be documented in the ED notes

  - Their Drug Chart must be completed

  - Wherever appropriate, VTE assessment must be completed and form kept in the notes

  - Medical SHO must be informed about the patient

The Emergency Physician In Charge (EPIC)

The EPIC will provide overall senior clinical leadership to the Emergency Department, thus ensuring:

- Delivery of safe and effective care for all patients

- Performance Standards are met

- Staff wellbeing

- Appropriate teaching / mentor support

- Definitive clinical judgement

- Senior medical liaison

- Role modelling of Trust values and behaviours

Who can undertake the role

- Senior Middle-grade (ST4 equivalent or above)

- There will be a named EPIC at all times. This will be indicated on the Allocation sheet

Base

- Majors area of the Emergency Department

Key Relationships

- ED NIC

- ED medical staff

- ED senior nursing staff

- Operational management team

- In-patient Specialty teams

- Senior management team

Responsibilities

Overall senior clinical responsibility for the entire Emergency Department to ensure safety, flow and performance. This will be achieved by…

Patient Safety

- Act as the resident clinical expert in support of junior medical staff/ACPs ensuring reviews are documented contemporaneously

- To provide direct clinical input into all priority and resus patients

- Regular clinical liaison (two hourly) with the NIC to review the department in terms of safety, flow and escalation requirements

- To ensure staff adhere to the appropriate tools and triggers as per the Escalation Policy when the Emergency Department is under significant pressure

- Take overall responsibility for review and interpretation of clinical interventions including sign off all ECG’s and blood gases performed on patients in the Majors area

Effective patient flow

- To be guided by the NIC in relation to activity within the Department

- To ensure all senior clinical staff work to optimum capacity to expedite effective flow

- To liaise with the in-patient specialty teams when delays have been identified in the clinical review of referred patients

- To provide high level negotiation input with Specialty teams as required

- To ensure any unacceptable delay is escalated to relevant peers/relevant Specialty Consultant (i.e. more than one hour)

- To ensure escalation processes are adhered to at all times advising senior management of any immediate and predicted risk

Staffing

- To provide overall clinical leadership within the ED

- To exemplify and champion professional behaviours within the ED team at all times

- To ensure all medical staff are fully conversant with and adhere to their respective roles and responsibilities

- To facilitate regular education, development and pastoral support to the ED medical team based on clinical need and risk assessment

- Review and amend the allocation of staff resource in the department, in conjunction with the Clinical Co-ordinator based on acuity and flow

- To ensure medical staff and ACP’s receive appropriate respite as required

- To provide regular review, assessment and deployment of the ED staffing rota, ensuring any gaps are identified and escalated accordingly

Handover

- Ensure all staff attend daily handover at 8 am, 3 pm and 9 pm

- To ensure all medical/ACP staff deliver and receive an appropriate clinical handover

- To provide senior clinical oversight in respect of any concerns raised at handover

Direct Patient Contact

- To provide overall senior clinical responsibility for all patients in the department utilising respective skills to expedite individual patient journeys when required

The Nurse-in-charge (NIC)

The SOP below identifies the roles and responsibilities of the NIC as a Clinical Co-ordinator (CCO), who can undertake said role, base within the department and Key relationships.

This SOP is currently under further development following recent changes

Hospital-wide policy

- Emergency Department (ED) will initiate all appropriate emergency investigations prior to admission.

- ED will also initiate all time-critical emergency treatment prior to admission.

- ED Staff should refer patients within 2 hrs of their arrival

- After referral for admission is made, duty of care passes to the accepting specialty.

- Following referral to specialty from ED, the specialty registrar / consultant will attend the ED within 30 minutes of referral. If the specialty cannot attend within 30 minutes, the patient will be transferred to the appropriate ward for review.

- Specialty opinions should be given by ST-3 level doctor or above.

- A bed request should be made as soon as admission is anticipated.

- Patients accepted for in-patient bed will be transferred with 30 min of acceptance.

- Stable adult patients considered for fast track admission must have a senior specialty / ED Consultant review (e.g. stroke patient).

- If patient with a GP referral letter to a specialty arrive in the ED, they should be seen by that team in the ED within 60 minutes of arrival, if deemed appropriate by the ED Consultant, even if they are not ‘expected’.

- Discharged patients who return within 7 days of surgery or a procedure, must be seen by the specialty team if they return with a direct complication of their surgery or procedure; e.g. wound infection / pain.

- When the waiting time to be seen by a doctor in the ED is estimated to be in excess of 3 hours, specialty teams may be contacted to review patients deemed likely for admission to their specialty (following review by an ED senior decision maker). It should be noted that this should be the exception rather than the rule and should be escalated to Gold On Call to authorise this decision.

- Patients who fulfil the specialty referral criteria (who may be suitable for discharge), can be referred directly by the ED Consultant to specialty without additional re review.

- Once a reasonable referral has been made by the ED to a specialty and the specialty feels that it is in the patient’s best interest to be managed by another specialty, then the responsibility of referring the patient to the other specialty lies with the first specialty and does not default back to the ED.

- If a patient clearly needs admission and two or more specialties cannot agree on who should accept the patient, this must be discussed at Consultant level. If this still cannot be agreed, the ED Consultant will decide which specialty the patient will be transferred to and the most appropriate clinical environment in cases of disagreement. The names of the consultants on call for these specialties should be documented in the ED notes for clarity of patient ownership.

Resus

- Critically ill patients in Resus will have assessment and resuscitation initiated by the Emergency Department. If the patient has been referred to a specialty, the speciality team should attend within a maximum of 30 minutes and remain with the patient for on-going care until stabilised.

- The review should be by specialty ST3 or above within 30 minutes of referral. The duty of care remains with the Emergency Department until the specialty attends.  If the specialty cannot attend within 30 minutes, escalation to specialty consultant level is required. (Review by a more junior doctor is not appropriate.)

- All genuine Resus patients should have a clear plan/diagnosis within 2 hours of entering Resus.  If this is not the case, the Emergency Department Consultant should be informed in addition to the consultant of the corresponding speciality.  If agreement still cannot be reached then the specialty consultant should have a direct conversation with the Emergency Department to resolve the issue in the patient’s best interest.

- Attached below is the SOP designed to provide guidance and support for the NIC of the Resus area;

This SOP is currently under further development following recent changes

Transfers out of the department

- Critically ill transfers from Resus should be initiated by and arranged by the Emergency Department. Speciality teams must attend and support if requested  e.g. AAA, STEMI, major trauma

- Non-critically ill patients requiring transfer to tertiary care should be seen and then referred by the appropriate speciality team e.g. renal by medicine, spinal by orthopaedic, vascular and paediatric surgery by general surgery.

Internal Trust transfers to LCH or Admissions from Skegness, Johnson Hospital and from Clinics

- The patient should be referred to the middle grade doctor of the appropriate specialty and the accepting doctor’s name documented in the patients’ notes prior to transfer.

- A clear plan for the admission and actions to be taken should be documented in the notes.

- The referring doctor should arrange and request any scans they deem appropriate for the care of the patient prior to transfer to ensure patient delays are minimised.

- Treatment plans should be written clearly in the notes and prescriptions/drug cards completed.

All Admissions:

- All acute admissions will be reviewed by the admitting consultant within a maximum of 14 hours of admission.

- All new patients admitted through the non-elective pathways must be seen by a senior clinician prior to transfer/discharge (ST3 or above).

- All admissions must have a resus status, ceiling of care and estimated date of discharge at/before consultant review.

- All patients referred during an on-call period must be seen by the admitting team and consultant on call, regardless of location e.g. coronary care/SAU/ICU/Emergency Department.

- A patient requiring speciality input must be seen by a consultant/registrar following referral

- All inpatient specialty referrals must be seen by a ST3 or above within a maximum of 24 hours, and have a plan of care documented and enacted.

- If, on admission a patient is found to have/develops a condition that it is in the patient’s best interest to be managed by another speciality then care will be transferred to that speciality.  If this cannot be agreed this should be escalated to the Divisional Management team.

- Patients who are immediately post-operative should be managed on a surgical ward wherever possible or, as a minimum, have daily senior surgical input and surgical nursing care.

- Any patient admitted under joint care of 2 specialities must be seen by both consultants and there must be a direct conversation and agreement documented between the consultants regarding the on-going Care Plan.

- All inpatient investigations should be same day whenever possible, or maximum delay of 24 hours.

Hospital at night (H@N)

- Hospital at Night includes the medical and surgical registrar, the surgical, orthopaedic and 3 medical T2 Doctors and the H@N Team Leader.

- All Doctors are expected to be working continuously and should report to the Team Leader once specific tasks are completed for allocation of further work.

- The Medical Registrar is the lead doctor and has the overall control of the team for all specialities.

- The Doctors are on-call for their speciality but can be re-allocated tasks by the Team Leader and Medical Registrar as required within their competences and work for H@N.  This includes review of patients not from their parent speciality.

- This cover extends across all wards (except paediatrics and Obstetrics & Gynaecology who have a stand-alone rota), including the Emergency Department and is aimed at best patient care for all patients, addressing the greatest risk to patient safety at the time.

Emergency Care Speciality Input in AMU, Daily 9am-5pm

- Patients on the Acute Medical Unit who have been referred to a speciality will be seen as soon as possible within normal working hours.

- Specialty patients must be seen and accepted by the appropriate speciality and actively “pulled” to that ward. They must be seen daily by a consultant of that speciality until transferred from the Acute Medical Unit.

- Speciality input to the Acute Medical Unit should be at least twice daily, e.g. am, pm

Emergency Care Input – Other Specialities

- Haematology patients should be phoned through to the Consultant Haematologist on-call 0800-2400hrs daily. Overnight referrals should be made before the night team leave the AMU.

- Neurology Referrals: E-referral

- Rheumatology Referrals: E-referral

- In the event of an ‘Urgent Referral’ the relevant consultant should be contacted via their mobile during normal working hours.

Weekend working

The Consultant speciality on-call for the weekend will see all the following patients:

- All sick patients as identified through handover

- Any new patients on base or paired outlying wards

- Any patient who is appropriate or for possible discharge

- Any patient for speciality review on the AMU.

The junior doctors for each floor will support the consultant as required.

Consultation:

This document needs approval from following individuals / groups…

Dr. XXXXXXXX, Medical Director

Dr. XXXXXXXX, CD, Emergency Care

ED Clinical Team

XXXXXXXXXX, Head of Nursing

XXXXXXXXXX, General Manager

Prof. XXXXXXXX, CD, Clinical Services

Mr. XXXXXXXXXXXX, CD, General and Vascular Surgery

Mr. XXXXXXXXXXX, CD, Orthopaedics

Mr. XXXXXXXXX, CD, ENT, Ophthalmology, Max Fax Surgery

Ms. XXXXXXXXXXX / Mrs. XXXXXXXXXXXXX, HOS, Ob-Gyn.

XXXXXXXXXXX, Director of Operations

XXXXXXXXXXX, Chief Operating Officer

# Appendix O:  Benefits Plan and Register

# Appendix P: Risk Register

Attached is a copy of the current risk register as at 3rd February 2022.

# Appendix Q:  Project Execution Plan

Removed - sensitive

# Appendix R:  Projects Leads CV’s

Removed - GDPR

# Appendix S:  Communications Plan

Pilgrim hospital Emergency Department transformation – outline communications plan

Introduction

In August 2019, during a visit to Pilgrim Hospital, Boston, Prime Minister Boris Johnson announced government funding to transform the emergency department.

Securing the funding was the first major hurdle and then the work began. We have been busy liaising with our staff in the department, with colleagues across the Lincolnshire health and social care system, with national bodies and with patient representatives, to start the process of coming up with a plan that will give us an Emergency Department that is fit for the future.

- Objectives

The aim of this communications plan is to support the transformation of the ED department and any connected works. Making sure that all colleagues, partner organisations and interested parties are kept up to date and informed in a timely manner.

This is a really exciting time for the department and the hospital and through our communications channels we can make sure this momentum and excitement is shared with our colleagues, partners, patients, visitors and the local community the hospital serves.

- Key audiences

- All Staff including:

  - ED staff

  - Other affected teams

  - Board

  - Staff side

  - All other colleagues

- MPs

- Healthwatch Lincolnshire, patient and third sector groups

- Local politicians including district and county councillors

- Health scrutiny committee and health and wellbeing board chairs

- Commissioners (CCGs, NHSEI and county council).

- Partner organisations (councils, EMAS, LCHS, LPFT).

- Regulators (NHSEI, CQC)

- Neighbouring trusts, councils

- GPs

- Public

- Patients and carers

- Trust members (1,300 interested members of the public)

- Contractors and business partners

- Any other interested parties

- Media – although the media are not the final target audience they provide a powerful voice.

Please also see Appendix A and B below.

- Key messages

The key messages will change as the programme develops.

We have already covered:

- the funding announcement when the Prime Minister visited and a few internal comms messages to keep colleagues updated (including through a Pilgrim ED newsletter)

- Column in the Boston Standard to let people know that work is still happening behind the scenes

- The unveiling of the artistic impressions and plans ahead of the planning application being submitted.

- Work to enable the transformation of Pilgrim Emergency Department is set to begin.

- Social media posts linking to the planning application on the Boston Borough Council website.

The next wave of comms externally will be around getting our full business case signed off by the DHSC.

A lot of the communication will then be focussed internally as we complete the enabling works.

This will be followed by a big internal and external media push when the works begin – with lots of regular updates as we come to key milestones through our staff comms, columns to local media and also through our social media channels.

Finally, once the works are completed we will do lots of comms for staff, invite the media to the official opening, we can do interviews with our execs, the ED teams, a tour of the department, patient feedback etc.

- Plan

Any messages shared externally, should first be made available to ULHT colleagues (particularly those directly affected). The plan below will be developed and extended as work progresses and messages are agreed.

We have lots of channels we can utilise, including:

Internal comms – all staff emails, newsletter (template drafted), weekly round up, ULHT Together Facebook page, exec blogs, videos, posters, intranet etc.

External comms – corporate social media accounts, press releases, stakeholder messages, website, monthly columns in local media, videos etc.

| Audience | Format or method | Message | Channel/ outlet | Timing | Comms Lead | Progress |
| --- | --- | --- | --- | --- | --- | --- |
| Staff | One off email | Funding announced and Boris visit | ULHT intranet Email Facebook Round up Blogs | August 2019 |  | Done |
| Public | Press release | Funding announced and Boris visit | ULHT website ULHT social media accounts and Press release Press release and media interviews | August 2019 |  | Done |
| Public | Column by A&E consultant | Work continues on project | Local media | March 2020 |  | Done |
| Staff | Staff update | Work is progressing | Weekly round up Newsletter intranet | July 2021 |  | Done |
| Staff | Staff update | Work is progressing | Weekly round up Newsletter Intranet | August 2021 |  | Done |
| Staff | Staff update | Work is progressing – these are the plans | ULHT intranet Facebook Round up Blogs Artist’s impression | From W/C 25/10/21 |  | Done |
| Public | Press Release | Work is progressing – these are the plans | Press release and media interviews Story on website Social media. Artist’s impression Stakeholder message | From W/C 25/10/21 |  | Done (social media ongoing) |
| Public/staff | Update | Plans have now been submitted for planning permission and are available here – link to council website | Update story on the website and social media | Early November 2021 TBC |  | Done |
| Public/Staff | Update | Enabling works are needed ahead of our ED build | Press release Story on website Social media ULHT intranet Email Facebook Round up Blogs Videos/pics | January 2022 |  | Done |
| Staff | Staff update | Work will/has begun | ULHT intranet Email Facebook Round up Blogs Videos/pics | TBC |  |  |
| Public | Press release | Work will/has begun | Press release – invite media Social media Videos/pics Stakeholder message | TBC |  |  |
| Staff | Staff update | Key milestones | ULHT intranet Email Facebook Round up Blogs Videos/pics | TBC as needed |  |  |
| Public | Updates | Key milestones | Social media Columns Videos/pics Stakeholder message? | TBC as needed |  |  |
| Staff | Staff update | ED is completed and open | ULHT intranet Email Facebook Round up Blogs | TBC |  |  |
| Public | Press release | ED is completed and open | Press release – invite media Stakeholder message and invitation Social media Columns Videos Pictures | TBC |  |  |

See the communications and engagement toolkit for more information. This also includes the pros and cons of corporate channels, different media and engagement techniques.

http://ulhintranet/communications-toolkit

# Appendix T:  Sustainable Development Management Plan (SDMP)

# Appendix U:  Project Team Meetings Terms of Reference

Pilgrim Hospital Urgent Care Project

Terms of Reference

1. Strategic Statement

The Pilgrim Hospital Urgent Care Project Project is established to manage developments to the Resuscitation Department (Resus) and the building of an Urgent Treatment Centre (UTC) as part of the funding for 20 health organisations to receive a share of £850M announced by the Prime Minister on 5th August 2019.  The work for this project was costed at £21.3M.

The project will oversee the development of the SOC through to FBC, establish a clear governance framework for the schemes, develop the design brief to go out to tender for contractors and oversee the project to completion.

2. Constitution

The Pilgrim Hospital Urgent Care Project will be managed under two groups.  Assurance that the project is being delivered will be undertaken by a Project Oversight Group (POG), chaired by the Chief Operating Officer, which is formed under resolution of the Trust Board of United Lincolnshire Hospitals NHS Trust.  This group will have financial decision making powers, delegated from the Trust Board, to appoint advisors and contractors to facilitate development of the business cases, design and construction.  However, business cases will go to the Trusts Capital and Revenue Investment Group.  System assurance will be via the Urgent Care Delivery Board.

Under resolution of the Project Oversight Group a Project Working Group (PWG) will be established.  This group will be a mix of management, facilities and clinical teams that will develop the FBC for the project.  The group will test any assumptions in the business cases and work to ensure robust planning that represent best value for money throughout the project.  This group will also consider staffing models for the new unit ensuring the integration of services between agencies.  The Chair of PWG will ensure input of content is considered, discussed and shared appropriately to members of both POG and PWG.

The meeting and reporting structure for the project is given in the appendix.

3. Membership

The POG and PWG will be comprised of all relevant parties within the Health and Care System within Lincolnshire who provide Urgent Care Services.  Meetings will take place fortnightly, alternating weeks.  Arrangements will be reviewed throughout the project and membership extended as required.

Membership will include:

| Project Oversight Group - Meets Fortnightly on Tuesdays | Project Working Group - Meets Fortnightly on Wednesdays |
| --- | --- |
| United Lincolnshire Hospitals NHS Trust | United Lincolnshire Hospitals NHS Trust |
| , Chief Operating Officer | , Deputy Director of Operations (Project Manager, Deputy Chair) |
| , Deputy Director of Operations (Project Manager, Deputy Chair) | , Consultant, Emergency Medicine |
| , Associate Director of Estates and Capital Planning (Deputy Chair) | , Consultant in Acute Medicine, PHB |
| , Assistant Director of Strategy and Change (Deputy Chair) | , Matron, Medicine |
| , Director of Estates and Facilities | , Deputy Chief Nurse |
| , Associate Director of Strategic Business Planning, Facilities | , Lead Sister, PHB ED |
| , Associate Director of Finance | , Capital Projects Manager |
| , Assistant Director of Finance | , General Manager, Medicine |
| , Divisional Managing Director for Medicine | , Operational Service Manager, ED |
| , Communications Officer | , Clinical Applications Engineer, Clinical Engineering |
|  | , Radiology |
| Lincolnshire Clinical Commissioning Groups | , Pathology |
| , Urgent Care Programme Director, Lincolnshire East CCG | , Staff Side |
| , Interim Chief Operating Officer, Lincolnshire East CCG |  |
|  | Lincolnshire Clinical Commissioning Groups |
| Lincolnshire Community Health Services | , Urgent Care Programme Manager, Lincolnshire East CCG |
| , Medical Director and Project Clinical Lead | , Senior Commissioning and Performance Manager, Lincolnshire East CCG |
| , Deputy Director of Operations |  |
|  | Lincolnshire Community Health Services |
| In addition - co-opted as required | , GP |
| , as Advisor to the Oversight Group | , Matron, PHB Urgent Care |
|  | , Senior Project manager |
|  | Lincolnshire Primary Foundation Trust |
|  | , Business manager |
|  | In addition - co-opted as required |
|  | , EMAS |
|  | Patient Representatives |
|  | Adult Social Care |

For a meeting to be quorate there must be input from the clinical as well as management teams.  The POG must include the Chief Operating Officer or deputy, a member of ULHT Clinical Teams and Management Teams and a member from CCG and LCHS.  For PWG to be quorate there must be a member of the ED clinical team, management team and a member of staff from LCHS.

Co-opted members will be requested to join the meeting as required.

4. Frequency

The Project Assurance  Group will convene on a fortnightly basis, the working group weekly.

5. Authority

The Project Oversight Group will be accountable to the Trust Board and Executive Team and will update the Urgent Care Delivery Board as required.  Summary Progress and Exception Reports will be produced weekly for Trust Board Meetings.

6. Administration

Will be provided to the group by Medicine Personal Assistant / Administrative Team with support from, PA to the Chief Operating Officer and, Administrator, Facilities.

Appendix A – Meeting and Reporting Structure

Terms of Reference

The Pilgrim ED oversight group – Workstream 1 – Decant phase

# Scope

The Pilgrim Hospital Emergency Department project is part of a programme of work to improve Urgent and Emergency Care.  It was established by the ULHT Trust Board in 2019 following approval of funding for the work.

To ensure progress on the project an SRO (the Trusts Director of Improvement and Integration) was put in place, with a supporting Oversight Group of senior leaders in CCG and partner organisations.  A project director (ULHT’s Associate Director of Strategic Projects) was asked to lead the underlying working group.  The reporting governance structure is given below:

Workstream 1 is one of five workstreams reporting to Pilgrim ED oversight Group with an aim   to represent all departments and system partners who have direct service requirements both clinical and non-clinical.

The workstream group will have responsibility and accountability to deliver;

- the temporary and/or permanent relocation options for the services within the designated accommodation for the demolition and new build Emergency department;

- alignment of decisions regarding utilisation of accommodation to the Trust’s clinical strategy and Covid 19 related plans;

- (Recovery) Coordination and oversight of plans regarding estates and accommodation developments on the Pilgrim sites;

- Co-ordination and communication to all staff and system partners.

# Purpose

# Work Stream 1

- Develop and design options for consideration to meet the needs of space/maintaining of service 24/7 and patient welfare to vacant the designated accommodation for demolition and the new build ED;

- Working with system partners LCHS and EMAS on the temporary location of the current Urgent Treatment Centre ensuring continuous 24/7 service connected to the existing Emergency Department until the completion of the project;

- Review of all current services in the designated area and provide options to Oversight Group via the Project Working Group.

# Membership

| Position | Organisation |  |
| --- | --- | --- |
| MD CSS – Workstream SRO | ULHT |  |
| Project Director | ULHT |  |
| Strategic Advisor | Consultant |  |
| Procurement | ULHT |  |
| Lead Matron – Outpatients | ULHT |  |
| TBC | LCHS |  |
| TBC | LCHS |  |
| TBC | ULHT |  |
| TBC | ULHT |  |
| TBC | ULHT |  |
| Lead Manager | ULHT |  |
| TBC | ULHT |  |
| TBC | ULHT |  |
| TBC | ULHT |  |
| TBC | ULHT |  |
| Fred Royales | ULHT |  |
| Wayne McIntosh | ULHT |  |
| Communications Officer | ULHT |  |

It is expected that members attend and when unable they will send a fully briefed deputy, who will be responsible for the communication within their respective division/Department.

The group will be expected to grow/reduce as decided by the SRO dependent on priority of proposals.

It is the responsibility and kindly requested of each of the attendees to provide regular updates to their respective internal departments and staff colleagues and all general communication to be agreed by Communication department.

# Quorate

Meetings will be considered quorate as a minimum the chair, or representative, nursing and estates.

The workstream reports into this Group for discussion/awareness/sign off. Monthly reports will be submitted to Trust Board and regular updates to NHSE/I

# Frequency

The meeting will meet fortnightly. Use of Microsoft teams will be available to all sites.

Terms of Reference

The Pilgrim ED oversight group – Workstream 2 – Review of proposed Design & Options appraisal

# Scope

The Pilgrim Hospital Emergency Department project is part of a programme of work to improve Urgent and Emergency Care.  It was established by the ULHT Trust Board in 2019 following approval of funding for the work.

To ensure progress on the project an SRO (the Trusts Director of Improvement and Integration) was put in place, with a supporting Oversight Group of senior leaders in CCG and partner organisations.  A project director (ULHT’s Associate Director of Strategic Projects) was asked to lead the underlying working group.  The reporting governance structure is given below:

Workstream 2 is one of the five Pre-mobilisation work streams reporting to Pilgrim ED oversight Group with an aim to represent all departments and system partners who have direct service requirements/dependencies both clinical and non-clinical.

The work stream group will have responsibility and accountability to deliver;

- Develop and review the scope and requirements for the design.

- Enabling works - Preparation of the site for the first stage of development.

- Identify and explore the different delivery model options and evaluate against an agreed set of criteria.

# Membership

| Position | Organisation |  |
| --- | --- | --- |
| Workstream 2 SRO | ULHT |  |
| Strategic Advisor | Consultant |  |
| Project Director | ULHT |  |
| Interim Capital Estates | ULHT |  |
| Procurement | ULHT |  |
| Procurement | ULHT |  |
| Matron – Estates & Facilities | ULHT |  |
| Kieron Davey | ULHT |  |
| TBC | ULHT |  |
| Ian Trevor | ULHT |  |
| TBC | ULHT |  |
| Communications Officer | ULHT |  |
| TBC | TBC |  |

It is expected that members attend and when unable they will send a fully briefed deputy, who will be responsible for the communication within their respective division/Department.

The group will be expected to grow/reduce as decided by the Lead SRO dependent on priority of proposals.

It is the responsibility and kindly requested of each of the attendees to provide regular updates to their respective internal departments and staff colleagues and all general communication to be agreed by Communication department.

# Quorate

Meetings will be considered quorate as a minimum the chair, or representative, nursing and estates.

The workstream reports into this Group for discussion/awareness/sign off.  Monthly reports will be submitted to Trust Board and regular updates to NHSE/I.

# Frequency:

The meeting will meet fortnightly. Use of Microsoft teams will be available to all sites.

Terms of Reference

The Pilgrim ED oversight group – Workstream 3 – Power and Utilities

# Scope

The Pilgrim Hospital Emergency Department project is part of a programme of work to improve Urgent and Emergency Care.  It was established by the ULHT Trust Board in 2019 following approval of funding for the work.

To ensure progress on the project an SRO (the Trusts Director of Improvement and Integration) was put in place, with a supporting Oversight Group of senior leaders in CCG and partner organisations.  A project director (ULHT’s Associate Director of Strategic Projects) was asked to lead the underlying working group.  The reporting governance structure is given below:

Workstream 3 is one of the five Pre-mobilisation work streams reporting to Pilgrim ED oversight Group with an aim to represent all departments and system partners who have direct service requirements/dependencies both clinical and non-clinical.

The work stream group will have responsibility and accountability to deliver;

- Review and provide options to address the low capacity availability currently at front of house, Pilgrim;

- Scope, design specifications, tender agreed solution to meet the needs for power, water, medical gases;

- Review and provide options to address the digital services sustainability and resilience at Pilgrim hospital;

- Co-ordination and communication to all staff and system partners.

# Purpose

# Work Stream 3

- Review of Power & Utilities capacity to meet the extra needs;

- Provide and support specifications for tendering;

- Digital Support Services options.

# Membership

| Position | Organisation |  |
| --- | --- | --- |
| Workstream 3 SRO | ULHT |  |
| Strategic Advisor | Consultant |  |
| Cliff Almond | ULHT |  |
| Procurement | ULHT |  |
| Procurement | ULHT |  |
| Matron – Estates & Facilities | ULHT |  |
| Kieron Davey | ULHT |  |
| TBC | ULHT |  |
| TBC | ULHT |  |
| Fred Royales | ULHT |  |
| Tony Woods | ULHT |  |
| Communications Officer | ULHT |  |

It is expected that members attend and when unable they will send a fully briefed deputy, who will be responsible for the communication within their respective division/Department.

The group will be expected to grow/reduce as decided by the Lead SRO dependent on priority of proposals.

It is the responsibility and kindly requested of each of the attendees to provide regular updates to their respective internal departments and staff colleagues and all general communication to be agreed by Communication department.

# Quorate

Meetings will be considered quorate as a minimum the chair, or representative, nursing and estates.

The workstream reports into this Group for discussion/awareness/sign off. Monthly reports will be submitted to Trust Board and regular updates to NHSE/I.

# Frequency:

The meeting will meet fortnightly. Use of Microsoft teams will be available to all sites.

Terms of Reference

The Pilgrim ED oversight group – Workstream 4 – Design & Build Tender

# Scope

The Pilgrim Hospital Emergency Department project is part of a programme of work to improve Urgent and Emergency Care.  It was established by the ULHT Trust Board in 2019 following approval of funding for the work.

To ensure progress on the project an SRO (the Trusts Director of Improvement and Integration) was put in place, with a supporting Oversight Group of senior leaders in CCG and partner organisations.  A project director (ULHT’s Associate Director of Strategic Projects) was asked to lead the underlying working group.  The reporting governance structure is given below:

Workstream 4 is one of the five pre-mobilisation workstreams reporting to Pilgrim ED oversight Group with an aim to represent all departments and system partners who have direct service requirements/dependencies both clinical and non-clinical.

The work stream group will have responsibility and accountability to deliver:

- Develop the scope, specifications and requirements through an established design team and the contractor;

- Agree the enabling works options and designs;

- Meet all compliance requirements of the contracting authority eg. HBN/BREEAM;

- Ensure Value for money through value engineering.

# Membership

| Position | Organisation |  |
| --- | --- | --- |
| Workstream 4 SRO | ULHT |  |
| Strategic Advisor | Consultant |  |
| Interim Capital Estates | ULHT |  |
| Procurement | ULHT |  |
| Procurement | ULHT |  |
| Matron – Estates & Facilities | ULHT |  |
| Kieron Davey | ULHT |  |
| TBC | ULHT |  |
| Ian Trevor | ULHT |  |
| TBC | LCHS |  |
| TBC | ULHT |  |
| TBC | ULHT |  |
| Fred Royales | ULHT |  |
| Tony Woods | ULHT |  |
| Communications Officer | ULHT |  |

It is expected that members attend and when unable they will send a fully briefed deputy, who will be responsible for the communication within their respective division/Department.

The group will be expected to grow/reduce as decided by the Lead SRO dependent on priority of proposals.

It is the responsibility and kindly requested of each of the attendees to provide regular updates to their respective internal departments and staff colleagues and all general communication to be agreed by Communication department.

# Quorate

Meetings will be considered quorate as a minimum the chair, or representative, nursing and estates.

The workstream reports into this Group for discussion/awareness/sign off. Monthly reports will be submitted to Trust Board and regular updates to NHSE/I

# Frequency

The meeting will meet fortnightly. Use of Microsoft teams will be available to all sites.

Terms of Reference

The Pilgrim ED Oversight Group – Work Stream 5 – FBC Preparation and Submission

# Scope

The Pilgrim Hospital Emergency Department project is part of a programme of work to improve Urgent and Emergency Care.  It was established by the ULHT Trust Board in 2019 following approval of funding for the work.

To ensure progress on the project an SRO (the Trusts Director of Improvement and Integration) was put in place, with a supporting Oversight Group of senior leaders in CCG and partner organisations.  A project director (ULHT’s Associate Director of Strategic Projects) was asked to lead the underlying working group.  The reporting governance structure is given below:

Workstream 5 is final piece of the pre-mobilisation work involved in developing the Pilgrim Hospital ED Project.  The group reports to the project working group with an aim to represent all departments and system partners who have direct service requirements / dependencies both clinical and non-clinical.

The workstream will have responsibility and accountability to deliver:

- Consolidation of other workstream deliverables in support of the FBC;

- To develop the FBC to a high standard, taking advice from HM Treasuries Green Book and supporting guidance;

- To provide regular updates of progress on the FBC to the Working Group for upward submission to the Oversight Group and SRO;

- Finalise and submit the FBC for approval through the Trust governance processes.

# Membership

| Position | Organisation |  |
| --- | --- | --- |
| Workstream 5 SRO | ULHT |  |
| Strategic Advisor | Consultant |  |
| Business Case Manager | ULHT |  |
| Interim Capital Estates | ULHT |  |
| Procurement | ULHT |  |
| Procurement | ULHT |  |
| Matron – Estates & Facilities | ULHT |  |
| Kieron Davey | ULHT |  |
| TBC | ULHT |  |
| Ian Rushton | ULHT |  |
| TBC |  |  |
| Communications Officer | ULHT |  |

It is expected that as and when meetings take place members attend or send a fully briefed deputy, who will be responsible for the communication within their respective division / department.

The group will be expected to grow or reduce as decided by the workstream SRO dependent on the work being done.

It is the responsibility and kindly requested of each of the attendees to provide regular updates to their respective internal departments and staff colleagues and all general communication to be agreed by Communication department.

# Quorate

Meetings will be considered quorate if, as a minimum, the chair, or representative, nursing representative and estates representative are in attendance.

The workstream reports into the Project Working Group for discussion, awareness and sign off.  Attached is the template for report completion.

Meetings will be called on an ad hoc basis.  This workstream is dependent on the other 4 workstreams and as such will be called as and when information becomes available.  Use of Microsoft teams will be available to all sites.

# Appendix V:  Premises Assurance Model

# Appendix W – ULHT Draft Green Plan

The attached is for information as requested.  This document is not yet an official ULHT document.

# Appendix X – Schedule of Accommodation and Derogations

# Appendix Y – ITT & Contracts

Removed - commercial

# Appendix Z – Equipment List

See estates annex

| Room # | Notes | Other Electronics | Other POWER | Other LAN | Medical devices as of 20/09/2021 | POWER sockets for MedDev | LAN sockets for MedDev | ICT | POWER ICT | LAN ICT |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Lobby 1 | Next to Main Entrance | Vending Machines In the future: Patient Kiosk | 6 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |
| Waiting Area 2 | Left side will be UTC waiting Area Right side ED waiting Area | Patient Display monitors (1x UTC and 1x ED side) Desirable: Speakers to call for patients. USB chargers for patients | 4 USB chargers | 4 | 0 | 0 | 0 | 0 | 0 | 0 |
| Wheelchair Waiting area 3 | N/A | USB chargers for patients | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Changing place 4 | N/A | Desirable: Speakers to call for patients. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Reception 5 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 4x PCs + 2 printers (1x UTC and 1x ED) + 2x Phones | 14 | 12 |
| Office UTC & ULH 6 | N/A | 0 | 0 | 0 | 0 | 0 | 0 | 4x PCs + circa 2 printers (1x UTC and 1x ED) + 2x Phones (1x general use - one for local use) To consider charging units for the Porter Radios | 16 | 12 |
| ACC WC 7+8 | N/A | Desirable: Speakers to call for patients. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Vending - Family Room 9 | N/A | Table + a sofa unit USB chargers for patients | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Nappy Change 10 | N/A | Desirable: Speakers to call for patients. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Triage 11 |  | 0 | 0 | 0 | 1 x VS900 Obs Monitor on the wall 1x Thermometer 1x Diag Set (ophth &oto) Mobile 1x Patient Couch | 3 | 2 | 1x PC No printer | 4 | 2 |
| Triage 12 |  | 0 | 0 | 0 | 1 x VS900 Obs Monitor on the wall 1x Thermometer 1x Diag Set (ophth &oto) Mobile 1x Patient Couch | 3 | 2 | 1x PC No printer | 4 | 2 |
| Obs/ Phlebotomy 13 |  | 0 | 0 | 0 | 1 x Patient Monitor with 3/5 ECG no CO2 1x Thermometer 1x mobile ECG 12 Lead 1x Blood Gas Analyser no printer required 1x Patient Trolley not x-rayable (ambulant patients) Glucose Meters Chargers 1x Resus trolley | 6 | 2 | 1x Printer for Blood forms 1x PC | 4 | 2 |
| Store 14 |  | General store no med equipment | 0 | 0 | Not done on 20/09 - is this LCHS?? |  |  | Not done on 20/09 - is this LCHS?? |  |  |
| Linen 15 |  | N/A | 0 | 0 | Not done on 20/09 - is this LCHS?? |  |  | Not done on 20/09 - is this LCHS?? |  |  |
| Consult/ Exam 16-23 |  | To mirror UTC from LCH. |  |  | Not done on 20/09 - is this LCHS?? |  |  | Not done on 20/09 - is this LCHS?? |  |  |
| ACCWC 31 |  | 0 | 0 |  | Hoist - wall mounted - Confirm with H&S Already in use at PHB | 0 | 0 | 0 |  | 0 |
| Paeds Waiting Area/Play area 32 |  | Info Monitor; DVD player, TV? And other children toys USB charging points for patients? | 4 | 2 | 0 | 0 | 0 | 0 | 0 | 0 |
| Paeds Triage 33 - going to be Store room / Drugs Room |  | 0 | 0 | 0 | Drug Fridge + Resus Trolley + IV poles + equipment for Charging | 14 | 2 | 0 | 0 | 0 |
| Paeds Consult Room 34-36 | Treated Like Major Rooms | TV + DVD facility | 4 | 2 | Patient trolleys - xrable Patient Monitors (CO2, ECG 12 lead, Printer) + therm on Wall Mounted Diagnostic Set confirmed no slave monitors No dedicated but will have to plug in: syringe drivers + volumetric pumps + US Ceiling mounted lights - TBC 1x nebuliser | 8 | 2 | No PCs - located in the staff base | 0 | 0 |
| Staff Base 37 |  |  |  |  | Central Station 1x monitor for 3x consul bays (wall mounted if possible) Blood Glucose Charging kits + charging for kids iPad | 6 | 1 | 1x PC for the HCW, 1x PC for the nurse, 1x PC for the Dr + 1 Printer + phone Charging Cabinets for iPad TBA ICT?? | 12 | 4 |
| PAED Store 38 - Going to be Triage/Phleb Room |  | Phlebotomy trolley | 0 | 0 | 1 x VS900 Obs Monitor on the wall + paeds SpO2 1x Thermometer 1x Diag Set (ophth &oto) Wall 1x patient trolley 1x Blood Gas Unit 1x Baby Scale + 1x Stand-on scale + height. 1x 12 ECG Diagnostics on wheels 1x Nebuliser | 8 | 2 | 1x PC + 1x Printer | 4 | 2 |
| RAS - Blue Zone |  |  |  |  |  |  |  |  |  |  |
| 2x Triage 39 and 40 but also Obs Phlebotomy 41 |  |  |  |  | Patient monitors (CO2+ print out 12 lead ECG) Wall 1x Blood Gas (one room only) Diagnostic on the wall Stand on Scale Xrayable Patient Trolley thermometer 2x 12 Lead ECG for diagnostic rolling stands - not fixed to this room 1x Resus Trolley | 8 | 2 | 1x PC in each + 1x printer for all 3 rooms | 4 | 2 |
| Staff Base 42 |  |  |  |  | Central Station 1x monitor for 3x triage bays (wall mounted if possible) Blood Glucose Charging kits + charging for ipads | 6 | 1 | 2x PC for the HCW, 1x PC for the nurse, 2x PC for the Dr + 1 Printer + 2x phone Charging Cabinets for iPad TBA ICT?? | 16 | 6 |
| Fit to Sit 43 | Triaged patients - receiving treatment - do not need trolleys - IV fluids/antibiotics/medication - monitor with obs units - rounds rather than continuous obs. Monitoring. 24x spaces. |  |  |  | 4x Obs Monitors on rolling stands Infusions - depending on patients (each with 1 socket + USB charger as patients are going to sit likely for hours to ensure that at least an IV pumps can be plugged in. | 24 + 1 USB each | 0 | 0 | 0 | 0 |
| Clean Procedure 44 | Major + Wounds |  |  |  | Patient monitors (Co2+ print out 12 lead ECG) Wall - central station (proper ecg one local anaesthetics Diagnostic on stand Xrayable Patient Trolley 1x thermometer 1x Ceiling light Major wounds | 4 | 2 | No PC no printer | 0 | 0 |
| CE/Gynae 45 |  |  |  |  | Obs Monitors VS900Wall - central station Diagnostic on stand Lithotomy Patient Trolley (leg up) 1x thermometer 1x gynae exam lamp can be ceiling | 4 | 2 | No PC no printer | 0 | 0 |
| ENT/ Eye room 46 |  |  |  |  | Obs Monitors VS900Wall - central station Diagnostic on stand Patient Trolley 1x thermometer 1x slit lamp wheelchair compatible 1x Logmar Chart Wall 1x tonometer 1x ENT examination lamp | 4 | 2 | No PC no printer | 0 | 0 |
| ACC WC 47 |  | 0 | 0 | 0 | 1x ceiling hoist? Ask M&H | 0 | 0 | 0 | 0 | 0 |
| DU 48 Sluice Room |  |  |  |  |  |  |  |  |  |  |
| Step Up Room 49-51 (mirror Resus cubicles) |  |  |  |  | 1x Multi parameter monitor with obs, 12x ECG, IBP, CO2, NIBP - all the specs. With Printer. 1x Pendant 1x diagnostic set mounted on pendant 1x manual defibrillator with C02 1x thermometer 1x nebuliser 1x Xrable patient trolley 1x patient warmer 2 for 2x cubicles 2 in RAS area) 2x oxylogs 2 volumetric pumps, one syringe 1x fluid warmers in each | 14 sockets on the pendant +4 sockets on trunking | 2x on the pendant | 1x PC | 4 | 2 |
| Drug Store Prep 53 also staff base for the 3x Step up rooms |  |  |  |  | 1x central monitoring + 1x printer Mindray | 4 | 2 | 1x printer + 1x PC +1x phone | 4 | 2 |
| Housekeeping Room 52 |  |  |  |  |  |  |  |  |  |  |
| Store 54 equipment store |  | 0 | 0 | 0 | IV poles fixed (infusion pumps) + Pumps docks 1x Drug Fridge + 1x Smart Thermometer | 20 | 0 | 0 | 0 | 0 |
| CU 55 - Clean utility | Used for safe assessment zone - mentally unwell patients | No med equip, no PCs. | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| Green Area - Diagnostics |  |  |  |  | 2 x wall mounted patient monitoring Resus trolley Contrast warmer Glucometer Weighing scales Waiting room chairs / CT Control room chairs x2 | 1 - Resus trolley 2 x patient monitoring | 0 | 2 x PC's (CT console), Phone | 6 x power | 6 X LAN |
| 6x Cubicles - 56-61 | Rapid Assessment Cubicles (RAIT) - patients come straight from ambulances | 0 | 0 | 0 | 1x Xrable trolleys 1x patient monitors (full specs) wall mounted 1x ceiling mounted patient exam lamps wall mounted diag sets 2x stand on scale for all 6 rooms 1x resus trolley for 6x cubicles 2x nebulisers for all 6x rooms 1x hoist for the area |  |  | 1x PC each room no printers |  |  |
| Staff Base 62 | 0 | 0 | 0 | 0 | 1x Central monitor 1x Blood Gas machine | 4 | 2 | 1x printer + 4x PCS (2x Dr, 1x HCW + 1x Nurse) + 1x phone line + 1x charging station for BM and ketone machines + changing plates for IPad | 16 | 6 |
| Shared Linen 63 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| ACC WC 64 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| CU and DU (65 + 66) |  |  |  |  |  |  |  |  |  |  |
| Light Green Command Zones |  |  |  |  |  |  |  |  |  |  |
| Resus Cubicles (67,68,69,70,71,72,75,78) | 78 is the Paeds dedicated Resus 73 dedicated bariatric Resus | 71 is to become DU 74 Resus in the middle with CU down 67-70 negative pressure |  |  | Slare screens for the negative pressure rooms in the lobby (1x power socket and 1x VGA from inside the room 1x Multi parameter monitor with obs, 12x ECG, IBP, CO2, NIBP - all the specs. With Printer. Pendant with two network points. 1x diagnostic set 777 wall mounted/draeger pendant 1x manual defibrillator with C02 - 1x thermometer 1x nebuliser 1x Xrable patient trolley 1x patient warmer for 2x cubicles 2 in RAS area) 1x Oxylog each neg pressure rooms 4x 3x Oxylogs for the standard rooms 4x LUCAS 2 volumetric pumps, one syringe 1x fluid warmers in each 1x Banana bed + hoist + M&H 1x 650 GE 1x stand on and chair scales for Resus + Baby Scale + 1x Resuscitaire for Transport 3x rapid infuser | 14 sockets on the pendant + 4 sockets on trunking | 2 | 1x PC no printers (in the staff area | 4 | 2 |
| Staff Base 81 |  |  |  |  | 2x Central monitors with 2x screens | 4 | 2 | 2x PC for nurses + 2x Dr + 1 HCW + 2x phones + 1 Printer + Ipad Chargers + BM Ketone Kits Charger | 20 | 8 |
| Drug Store 76 |  |  |  |  | 1x Blood Gas Machine 1x Drug Fridge + Thermometer Storage of equip | 12 | 2 | 1x PC (for Medusa Access) + Printer | 4 | 2 |
| Store 77 |  |  |  |  | Charging for IV pumps | 20 | 0 | 0 | 0 | 0 |
| EMAS Booking in 82 | PHP (prehospital handover practitioner) next to receptionists |  | 0 | 0 | IT | 0 | 0 | 2x PC (one with 2 screens PHP nurse) + Printer + Wrist Bands printers + Patient Labels | 8 | 4 |
| Lobby 83 |  | 0 | 0 | 0 | Weighing bridge | 0 | 0 | 0 | 0 | 0 |
| EMAS Trolley Bay 84,85+89+90 | Open plan space. |  | 0 | 0 | Ela to confirm with Abby Stryker (check power sockets) 2x Mobile Obs Monitor | 2 | 0 | 0 | 0 | 0 |
| CBRN Store 86 - Decon Zone |  |  |  |  |  |  |  |  |  |  |
| Command Zone79 | Zone for Consultant and Nurse in Charge + Coordinator | 0 | 0 | 0 | 2x central Monitoring for the entire department (RAS area - WHOLE ED dept). 2x from SITE bed space capacity 4x monitors screen. | 8 | 4 | 2x Dual Screen PCs + + 1x PC single monitor (triage) + 3 phone lines (Nurse + Consultant + Coordinator Assistant) + 1x printer. | 12 | 6 |
| Body Viewing 91 | sockets for relative |  | 2 | 0 | 2x Central monitors with 2x screens | 0 | 0 | 0 | 0 | 0 |
| Relatives Rooms | TV Screen potentially calming patients ? | Charging points? | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |
| ACC WC 93 | 0 |  | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |
| MAJORS |  |  |  |  |  |  |  |  |  |  |
| 11x Cubicles 94-105 includes | 104 will become DU/CU - and 107 currently DU CU will become a cubicle |  | 0 | 0 | Xrable Trolley Obs Machines Wall mounted - Central Station 1x Diag Sets 1x Ceiling exam Lights ECGs - 12 lead portable not in every room Scales but not in each room 2x Resus Trolleys around the staff base area Hoists and Banana Bed - confirm with H&S incl location 1x LUCAS | 8 | 2 | No PCs no printers | 0 | 0 |
| 1x safe assessment/DNV + Ensuite 101 | Bariatric | 0 | 0 | 0 | bariatric room ceiling hoist bathroom and room itself M&H Xrable Trolley Obs Machines Wall mounted - Central Station 1x Diag Sets 1x Ceiling exam Lights ECGs - 12 lead portable not in every room Scales but not in each room 2x Resus Trolleys around the staff base area | 8 | 2 | No PCs no printers | 0 |  |
| Housekeeping 106 |  |  |  |  |  |  |  |  |  |  |
| DU/CU 107 now |  |  |  |  |  |  |  |  |  |  |
| Staff Base 108 |  |  |  |  | BM Kit Chargers + IPad Charger + 1x Central Station 2 monitors | 8 | 2 | 5x PC + 1 Printer + 3x phone lines (high volume of referrals) | 18 | 6 |
| Drug 109 |  | 0 | 0 |  | 1x Drug Fridge + fridge thermometer Blood Gas Analyser US + infusion + bladder scanner + ECG 12 lead | 20 | 2 | 1x PC with a printer PATIENTS GET ADMITTED - photocopy notes - THESE PRINTERS ARE TO BE SEPARATE - need to sit in own dedicated areas - ICT TO CONSIDER THIS | 4 | 2 |
| Store room 110 |  |  |  |  | Medical Equipment's | 20 | 0 | 0 | 0 | 0 |
| Linen Room 111 |  |  |  |  |  |  |  |  |  |  |
| Staff Rest Room 112 |  |  |  |  |  |  |  |  |  |  |
| Staff Toilets 113 2x |  |  |  |  |  |  |  |  |  |  |
| ACC WC 114 |  |  |  |  |  |  |  |  |  |  |

# Appendix AA – CIA Model

# Appendix AB – Schedule of Accommodation & Derogations

# Appendix AC – FB Forms

# Appendix AD – BREEAM Assessment Report

# Appendix AE – MMC Utilisation Assessment Tool

# Appendix AF – Post Project Evaluation Plan

# Appendix AG – Social Value Plan

Removed GDPR

# Glossary

| CCG | Clinical Commissioning Group |
| --- | --- |
| CT | Computed Tomography. An X-ray image made using a form of tomography – a moving x-ray source to build a 3 dimensional image of the body |
| ED | Emergency Department (formerly Accident & Emergency or A&E) |
| EMAS | East Midlands Ambulance Service |
| EPIC | Emergency Physician in Charge |
| ETTF | Estates, Technology, Transformation Fund |
| FBC | Full Business Case. The FBC is the final of three business cases required for major capital projects. It deals with securing the solution for the project in terms of procuring the best VfM solution, contracting the deal and ensuring successful delivery |
| HBN | Health Building Notes. Produced by the Department of Health and Social Care these are a series of documents outlining best practice guidance for new healthcare buildings. HBN 15-01 pertains to Emergency Departments |
| LCHS | Lincolnshire Community Health Services NHS Trust |
| LPFT | Lincolnshire Partnership NHS Foundation Trust |
| Majors | Patients who exhibit signs of being seriously ill but are not in immediate danger of life or limb will be triaged to "majors" |
| Minors | Patients who need some investigation or treatment for an injury but are unlikely to be admitted |
| NEWS | National Early Warning Score. NEWS is a tool developed by the Royal College of Physicians which improves the detection and response to clinical deterioration in adult patients and is a key element of patient safety and improving patient outcomes |
| OBC | Outline Business Case. The OBC is the second of three business cases required for major capital projects. It plans out the scheme in terms of determining potential value for money, preparing for a potential deal, ascertaining affordability and funding requirements and planning for successful delivery |
| ONS | Office for National Statistics |
| Primary Care Streaming | A service operated by primary care alongside the ED. Patients presenting with conditions suitable for GP surgeries are redirected from the ED to the streaming service |
| RAT | Rapid Assessment and Treatment |
| Resus | An area of the ED where people are taken if they need life-saving treatment immediately |
| SDEC | Same Day Emergency Care. The provision of same day care for emergency patients who would otherwise be admitted to hospital. |
| SDMP | Sustainable Development Management Plan |
| SOC | Strategic Outline Case. The SOC is the first of three business cases required for major capital projects. It scopes the scheme in terms of the case for change and developing a preferred way forwards |
| STP | Sustainability and Transformation Partnership. These areas were created all over England and bring local health and care leaders together to plan the long-term needs of local communities |
| ULHT | United Lincolnshire Hospitals NHS Trust |
| UTC | Urgent Treatment Centre |
| VfM | Value for Money |