## Sheet1
Appendix A: October 2016 Integrated Strategic Risk Register and Board Assurance Framework
2016/17 Assurance Framework: October2016
Ref | Strategic Outcome | Strategic Risk | Potential Cause and Impact | Grade (including change in risk) |  |  | Key Controls | Mitigating actions | Three Lines of Defence |  |  | Gaps in control/assurance | Completion Date for Actions | Responsible Director | Escalation
|  |  |  | L | S | Rating |  |  | First | Second | Third
S01 | Strategic Objective: Consistently high quality and safe patient care
S01:1.1 | Positive patient experience | Failure to provide good quality and safe service | Cause PUncontrolled urgent care demand, exceeding capacity PEfficiency programme impact upon safety or reduce patient safety PInadequate staffing levels | 4 | 4 | 16 Very High Risk | Quality Strategy | • SQD/safety thermometer data • RCA of SUIs • Ward triangulation metrics • Daily review of nurse staffing • Falls reduction plan • Sepsis reduction plan • Specialty governance reviews • Hygiene improvement plan • 7 day service plan • Patient safety walkrounds • Whistleblowing policy • Nursing workforce plan • Urgent care delivery plan including beds | • Quality metrics in monthly business unit reviews • Quality Strategy | • Quality report to Board • Audit of Quality Account • Reports from HR and OD Committee • Annual nursing review • Patient experience, safety and mortality committee reports escalating to QGC | • Reports from QGC to Board • Reported elsewhere • Quality monitoring with CCG • NHSI external review (IDM) • Contract quality review with CCG | • Implementation of hygiene improvement plan, housekeeping resource • QIAs not yet completed • Insufficient backlog maintenance investment • Absence of investment in 7 day service plan • Unclear role of CEC for accountability | MTP to be produced The 2021 Programme will outline the key delivery milestones to be tracked for delivery actions required to mitigate the strategic risk. | Director of Nursing | No change Reviewed by Quality Governance
Impact PPoor patient experience and standards of care PLoss of reputation PFinancial penalties PRegulatory intervention/action
S02 | Strategic Objective: A clinically responsive organisation
S02:2.1 | Openness and transparency | Failure to provide good quality and safe service | Cause PFailure to meet quality strategy standards PInadequately maintained or obsolete infrastructure PHarm or error resulting from a failure to meet safe and responsive standards | 3 | 4 | 12 High Risk | Clinical Governance | • Clinical Strategy/LHAC/STP • Nurse recruitment and retention plans • Service review programme • Patient experience strategy • Patient experience committee • Staff engagement plan • Leadership programme • Job planning • Appraisals • Service improvement programme | Patient Safety and Clincial Effectiveness Assurance Report. Quality Report. Medicines Safety Report. | • STP/LHAC/MTP update • Reports from HR and OD Committee • Reports from FSID • HR/OD report | Reported elsewhere • LHAC Programme Board • Patient experience committee reports to QGC | Gaps in control • LHAC implementation delayed • Trust’s medium term plan not yet finalised • Service review programme just initiated • Key care pathways not yet identified for review (STP) Gaps in assurance • STP governance structure • Clinical Strategy implementation governance arranged | MTP to be produced The 2021 Programme will outline the key delivery milestones to be tracked for delivery actions required to mitigate the strategic risk. | Director of Operations | No change Reviewed by Quality Governance
Impact PPoor CQC rating PLoss of reputation PRegulatory intervention/action PSignificant failure of services due to prolonged loss of infrastructure
S03 | Strategic Objective: Services shaped around patients needs
S03:3.1 | Efficient and effective services | Failure to deliver change / transformation | Cause PFailure to deliver the Trust’s clinical strategy/LHAC PFailure of clinical services to plan for the future and failure to modernise major care pathways | 4 | 4 | 16 Very High Risk | Clinical Strategy | • Clinical Strategy/LHAC/STP • Nurse recruitment and retention plans • Service review programme • Patient experience strategy • Patient experience committee • Staff engagement plan • Leadership programme • Job planning • Appraisals • Service improvement programme | • LHAC Programme Board • Patient experience committee reports to QGC CSIG | • STP/LHAC/MTP update • Reports from HR and OD Committee • Reports from FSID • HR/OD report • CSIG | Reported elsewhere • LHAC Programme Board • Patient experience committee reports to QGC | MTP to be produced Currently shaping and setting up the 2021 Programme to deliver the MTP priorities. | MTP to be produced The 2021 Programme will outline the key delivery milestones to be tracked for delivery actions required to mitigate the strategic risk. | Medical Director | No change
Impact PUnsustainable services PPoor patient experience PPoor delivery of performance standards
S03:3.2 | Efficient and effective services | Failure to mainain effective partnerships | Cause PFailure to plan collectively with local CCGs, Providers and Network providers PFailure to secure collaborative provision of service PFailure to provide adequate support for education PFailure to foster good potential relationships | 3 | 4 | 12 High Risk | Communication Strategy | Developing partnership working. Stakeholder management | Monthly updates to the Trust Board including progress against key controls. |  |  | MTP to be produced Currently shaping and setting up the 2021 Programme to deliver the MTP priorities. | MTP to be produced by October 2016. The 2021 Programme will outline the key delivery milestones to be tracked for delivery actions required to mitigate the strategic risk. | Medical Director | No change
Impact PUnsustainable services in Lincolnshire PLoss of income PLoss of reputation
S03:3.3 | Efficient and effective services | Failure to provide and maintain as statutorily required, premises where care and treatment are delivered from that are clean, suitable for the intended purpose, maintained and where required, appropriately located, in accordance with the NHS Constitution, CQC regulations and other statutory legal duties. | Cause P Failure to plan effectively to deliver the built environment required for modern services PFailure to meet built environment statutory standards and best practice guidance PFailure to deliver a rolling programme of improvements PFailure to align current estates model to future clinical redesign Failure to invest in the built environment infrastructure to a sufficient level in both capital replacement and revenue maintenance over a prolonged period to ensure safety and reliability is assured | 4 | 4 | 16 Very High Risk | 1. Backlog/ Maintenance Capital and Revenue Investment 2. Estates Strategy 3. Safety Governance Assurance Delivery of Revenue Compliance Plan 4. Quality Governance Assurance | • Delivery of 16/17 capital backlog investment programme. • Development of 17/18 and 5 year capital backlog investment programmes. • Delivery of 16/17 revenue maintenance resources. • Development of 17/18 and on-going revenue resources plans. • Delivery of Draft Technical Estates Strategy. • Estates Strategy alignment with Clinical Strategy, including input to LHAC. • Sale of land to release resources. • Re-quantification of backlog maintenance scale to support investment planning. | 1, 2, 3 & 4. Progress monitored through estates program governance reporting to Director of Estates and Facilities. | 1. Estates Capital Progress reporting to Trust IPB. 2. Progress Reporting to Estates Environment Committee & LHAC Estates Programme Board. 3. Progress Reporting to Estates Environment Committee, Trust IPC and Trust HSC. 4. Progress Reporting to Estates Environment Committee & Trusts Sustainable Development Committee. | 1,2,3 &4 Estates Committee report to FSID. 1,2,3 &4 Estates National Reporting requirements through NHS PAM – for Trust Board Governance, National Estates performance data submissions (ERIC) and Lord Carter estates productivity and efficiency. | Gaps in control • Inadequate backlog maintenance funding capital/ revenue • Estates Strategy not complete • LHAC implementation/ clinical strategy delayed • Re quantification of backlog maintenance not yet complete Gaps in assurance • Programme management resources • Compliance evidence capture limited by revenue availability | 1. 16/17 financial year 2. draft 2016/17, Land Sales 16/17, 17/18, backlog re quantification 16/17 fin year 3. Revenue Compliance Plan 16/17 and on-going 4. EFM Quality 16/17 & on-going Energy and Sustainability 16/17 & On-going | Director of Estates and Facilities | Changes made Reviewed by FSID
|  |  | Impact PUnsustainable services in Lincolnshire PLoss of income PLoss of reputation Potential to harm patients, Staff and Visitors, including prolonged outage and loss of clinical facility impacting on patient safety Failure to comply with legal requirements leading to prosecution |  |  |  |  | • Electrical Infrastructure. • Mechanical Infrastructure. • Water Safety. • Asbestos Management. • Fire Safety. • EFM Quality Patient Environment - food/ cleaning/ physical environment • Energy and Sustainability
S04 | Strategic Objective: Skilled, competent and motivated workforce
S04:4.1 | Sustainable service delivery | Failure to sustain adequate workforce | Cause PPoor workforce planning PPoor workforce intelligence systems PRecruitment and retention difficulties in “hard to get” skills PPoor recognition and reward mechanisms PAbsence of new ways of working | 4 | 4 | 16 Very High Risk | Workforce planning | • Appraisal system • Core learning • Nursing recruitment and retention plan (including agency reduction) • Engagement programme • Leadership charter • Leadership development programme • Medical staff improvement programme • Job plans | Monthly updates to the Trust Board including progress against key controls. | • HR and OD report to Board • HR and OD Committee report • Staff survey action plan • Annual nurse establishment review • Pulse check review by ET |  | Gaps in control • Low appraisal and core learning compliance Gaps in assurance • Lack of assurance and compliance with Trust values and behaviours • Medical staff improvement programme | MTP to be produced by October 2016. The 2021 Programme will outline the key delivery milestones to be tracked for delivery actions required to mitigate the strategic risk. | Director of HR | No change Reviewed by HR&OD
Impact PFailure to deliver sufficient capacity to meet contracted obligation PPoor patient experience and outcomes PPoor CQC rating, regulatory action PLoss of reputation
S05 | Strategic Objective: Performance Improvement
S05:5.1 | Continuous improvement | Failure to sustainan engaged workforce | Cause PLow levels of engagement, health and well being and satisfaction PInadequate training, appraisals and development PInadequate recognition of staff PNon adherence to Trust values and behaviours PInconsistent leadership | 3 | 4 | 12 High Risk | Staff Engagement | • Leadership development • Recognition strategies • Effective appraisals • Embedding values and behaviours | Monthly updates to the Trust Board including progress against key controls. |  |  | MTP to be produced Currently shaping and setting up the 2021 Programme to deliver the MTP priorities. | MTP to be produced by October 2016. The 2021 Programme will outline the key delivery milestones to be tracked for delivery actions required to mitigate the strategic risk. | Director of HR | No change Reviewed by HR&OD
Impact PPoor patient experience and outcomes PLoss of reputation PPoor recruitment and retention prospects PPoor CQC results
S05:5.2 | Continuous improvement | Failure to maintain operational performance | Cause PFailure to deliver contractual/national performance targets PFailure to reduce delayed transfers of care PFailure to collect and report accurate data | 4 | 4 | 16 Very High Risk | Performance Management | • Urgent care plan (including bed capacity) • Lincolnshire SRG • Performance targets for CCGs/other providers in 2016/17 contract • Contract delivery plan • Winter plan • Urgent care improvement programme (including beds and QF3) • Cancer improvement plan • Performance Management Framework • Agreed local trajectories in contract with dependent target for CCSs/other trusts • SRG recovery plans • Data Quality Strategy | Performance Review • Contract Assurance Board • Business Unit business review meetings • SRG minutes • Planned Care Board | • Performance report • FSID report to Board | CCGs | Gaps in control • Insufficient bed capacity • No market repatriation plan • Unclear lines of accountability for CDs • Below trajectory perf in Q2 for cancer, A&E and Diagnostics. High risk of non delivery of RTT in July Gaps in assurance • Data Quality reporting | 2016/17 urgent delivery plan agreed and resolved including bed plans. CMG/CEC role dfinition to be considered by TB Revised opening hours for GDH A&E to release Med staff | Director of Operations | No change Reviewed by FSID
Impact PIntervention PLoss of STF and/or fines/penalties PLoss of reputation PPoor quality and patient experience PFailure to meet contractual obligations
S06 | Strategic Objective: Financial stability and recovery
S06:6.1 | Value for money | Failure to achieve financial sustainability | Cause • Failure to deliver the financial plan • Failure to manage historic debt • Failure to deliver required levels of efficiency gain • Loss of market share/failure to regain market share • Failure to deliver contract with CCGs including application of financial penalties • Failure to control agency costs • Failure to deliver the STF | 4 | 4 | 16 Very High Risk | Two-year Operational and Financial Plan | • Agreement of long term financial model. • Financial Strategy • Lines of financial accountability • Financial reporting to CEC, FSID and TB • Contract delivery plan • Urgent care delivery plan • Cancer, A&E plans • Efficiency programme • Business Unit review programme • Agency reduction plan • Liquidity plans agreed • FIP • Nursing recruitment strategy • Medical staff strategy | • Financial performance report • FSID report to Board • Efficiency programme update • Performance report • FIP | • Contract Assurance Board • Agency spend performance review by ET • FIMS return to NHSI • Efficiency programme overview by ET, CEC and CMB • Financial report to ET • IDM (NHSI) • Regular financial input to CMB • STF mitigation plan required | CCGs | Gaps in control • Gaps in delivery of efficiency programme • Long term efficiency programme not identified • Agency costs off trajectory for nursing • No market repatriation strategy Gaps in assurance • I &E forecast 2016/17 • Failure to achieve STF Funding | MTP to be produced 2017-18 Operational and Financial Plan outline report to November Board. | Director of Finance | Changes made Reviewed by FSID
Impact • Trust goes into administration, external intervention, regulatory action • Individual services not sustainable • Loss of reputation • Insufficient cash to be a going concern • Continual failure to deliver control total
Key
Risk Rating Key / Source - Risk Management Policy
Rating Change
No change in risk rating from previous version of assurance framework
Risk rating has been downgraded from previous vesion of assurance framework
Risk rating has been increased from previous version of assurance framework
| Lead officers will be asked to verify the status of each risk identfied within the Assurance Framework and the following colours will identify whether a risk has been updated. |  |  |  |  | Response received No changes required
Response received Amendments required